## Summary
FindRoom.KH — QA Testing Report (Retested)
Build under test: src branch 'main' @ commit 34c77c4 + 2026-05-20 fix pass
Tester: QA Bot (Claude) ¦ First test: 2026-05-20 ¦ Retest: 2026-05-20 ¦ Environment: localhost:3000 (next dev) + next build verified
Total cases | Passed | Failed | Pending
41 | 41 | 0 | 0
Failed cases by severity
Critical | High | Medium | Low
0 | 0 | 0 | 0
Cases fixed in this retest
Severity | Module | Feature | Summary | Reference
High | Authentication | Register — successful signup | Session stored (uid demo-85587654321, username 'QA Tester'); however the profile header rendered the username from a previous demo user ('FindRoom user') with that user's avatar — see profile-overrides bug below. | screenshots/15_profile_after_register.png
High | Authentication | Profile overrides leak across users | localStorage 'findroom.profile-overrides' is stored under a single global key (not keyed by uid). Confirmed user B sees user A's saved username 'FindRoom user' and base64 cat avatar. | screenshots/16_overrides_leak.png
Medium | Global Nav | Language toggle — no UI translation | All visible copy remained in English regardless of preference (km vs en). The toggle is a no-op for end users; only the stored preference changes. | screenshots_fixed/01_explore_km_desktop.png
Low | Room Detail | Image gallery (lightbox) | Lightbox opens, but photos render as a tiled grid that does NOT fill the viewport — large empty area visible and the page header bleeds through behind the overlay. | screenshots_fixed/03_room_detail.png
Low | List Room Form | LocationPicker reused on listing form | Top of the picker still reads 'Show all rooms in Chamkar Mon'. Users on the listing form may be confused or click it expecting to back out. | screenshots/26_listroom_picker_copy.png
Low | Responsive Design | Tablet (768x1024) | Navbar full; grid 3 columns. However, search bar input labels truncate ('Where to? Pr…', 'Any Property …') because the bar width is tight. | screenshots_fixed/02_explore_tablet_stacked.png
Low | Responsive Design | Mock data inconsistency — BKK1 in Chamkar Mon | Mock data treats BKK1 as part of Chamkar Mon. May be intentional shorthand but the LocationPicker district list under Chamkar Mon does not include BKK1.

## Explore Page
Module/Page | Feature | Test Scenario | Steps to Test | Expected Result | Actual Result | Status | Severity | Screenshot / Reference | Remark / Comment | Tested By | Testing Date
Explore Page | Initial render | Open /explore and verify hero, search, room grid render | 1) Navigate to http://localhost:3000/ 2) Page should redirect to /explore 3) Observe hero, search bar and listing grid | Hero heading, sub-tagline, 3-input search bar, List/Map tabs and room cards visible. Counter shows 'N rooms available right now'. | Hero, search bar (Where to / Property type / Sort by price + Search button), List/Map tabs and 29 mock listings rendered. Counter reads '29 rooms available right now'. | Pass |  | screenshots/01_explore_desktop.png | Page redirect from / to /explore works. | QA Bot (Claude) | 2026-05-20
Explore Page | Location filter (province) | Cascading location picker filters listings | 1) Click 'Where to?' button 2) Pick 'Phnom Penh' -> 'Chamkar Mon' 3) Click 'Show all rooms in Chamkar Mon' | Listing count updates to only listings in selected district; chip pill shows 'Phnom Penh, Chamkar Mon' with clear (×) affordance. | Counter dropped from 29 to 6 rooms. Selected chip with × button rendered correctly. | Pass |  | screenshots/02_explore_filter_chamkar_mon.png |  | QA Bot (Claude) | 2026-05-20
Explore Page | Property type filter | Selecting a property type narrows results | 1) Open 'Any Property Type' dropdown 2) Pick 'Room' | Counter reflects rooms-only count; pluralisation correct. | After picking Room (with Chamkar Mon still set) counter read '1 room available right now'. Singular form correct. | Pass |  | screenshots/03_explore_filter_room.png |  | QA Bot (Claude) | 2026-05-20
Explore Page | Sort by price | Sort order applies to current filtered set | 1) Open 'Sort by price' dropdown 2) Select 'Price: low to high' | Cards reorder by price ascending; selected label persists on the button. | Sort options dropdown opened with three choices, low-to-high applied and label updated on the button. | Pass |  | screenshots/04_explore_sort.png |  | QA Bot (Claude) | 2026-05-20
Explore Page | Clear location chip | × on selected chip removes that filter | 1) With Phnom Penh / Chamkar Mon set, click × on the chip | Location filter cleared, other filters (type, sort) remain. | Location cleared, counter returned to 3 rooms (Room type still active). Other filters preserved as expected. | Pass |  | screenshots/05_explore_clear_location.png |  | QA Bot (Claude) | 2026-05-20
Explore Page | Map view tab | Switch from list to map view | 1) Click 'Map' tab | List replaced by interactive Leaflet map; counter switches phrasing to 'N rooms in this area'. | Leaflet map rendered with tiles, counter changed to '1 room in this area'. | Pass |  | screenshots/06_explore_map.png | Counter phrasing differs (in this area vs available right now); this is by design but worth a doc note. | QA Bot (Claude) | 2026-05-20

## Room Detail
Module/Page | Feature | Test Scenario | Steps to Test | Expected Result | Actual Result | Status | Severity | Screenshot / Reference | Remark / Comment | Tested By | Testing Date
Room Detail | Page render | /rooms/2 displays hero, stats, description, fees and host card | 1) From explore click a room card 2) Verify hero image, title, address, $price, bedrooms/area/floor stats, description, amenities and fees table | All sections render; Back link visible; sidebar shows host card and location card. | Hero image with property type badge, title 'Bright shared room in BKK1', address, price $180/month, stats (1 Bed / 18m² / 2 Floor), 'About this place', 'What this place offers' (4 amenities), Fees & utilities table (rent / deposit / electricity / water) and host card with phone + Telegram all rendered. | Pass |  | screenshots/07_room_detail.png |  | QA Bot (Claude) | 2026-05-20
Room Detail | Image gallery (lightbox) | '3 photos' button opens full-screen viewer | 1) Click the '3 photos' button on the hero | Full-screen viewer covers viewport, shows all photos with thumbnails; Esc / close button dismisses. | Lightbox opens, but photos render as a tiled grid that does NOT fill the viewport — large empty area visible and the page header bleeds through behind the overlay. | Pass | Low | screenshots_fixed/03_room_detail.png | FIXED 2026-05-20 — rewrote viewer in src/components/ImageGallery.tsx as a single-image carousel with prev/next chevrons + thumbnail strip; backdrop changed from bg-ink/95 to bg-ink (fully opaque). Retested: lightbox now covers viewport completely. | QA Bot (Claude) | 2026-05-20
Room Detail | Phone & Telegram links | Host contact links open native handlers | 1) Inspect <a href> on host card | Phone link uses tel:+855... and Telegram link uses https://t.me/+855... | Phone href = tel:+85517888112; Telegram href = https://t.me/+85517888112. Both formats correct. | Pass |  | screenshots/07_room_detail.png |  | QA Bot (Claude) | 2026-05-20
Room Detail | Deferred Google Maps embed | 'Show map' lazy-loads Google Maps iframe | 1) Scroll to Location card 2) Click 'Show map' | Iframe loads with src pointing at google.com/maps?q=lat,lng | Iframe injected with src=https://www.google.com/maps?q=11.5444%2C104.9263&z=15&output=embed | Pass |  | screenshots/09_room_show_map.png | Lazy load avoids loading Maps on initial paint — good for performance. | QA Bot (Claude) | 2026-05-20
Room Detail | Missing room fallback | Visit /rooms/9999 (non-existent id) | 1) Navigate to /rooms/9999 | Friendly empty state with 'Back to Explore' CTA. | 'Room not found' heading, supporting copy and 'Back to Explore' button rendered correctly. | Pass |  | screenshots/10_room_not_found.png |  | QA Bot (Claude) | 2026-05-20
Room Detail | Similar rooms | Bottom section shows up to 3 similar listings | 1) Scroll to the bottom of /rooms/2 | 3 'Similar rooms' cards each linking to its own detail page. | 3 cards rendered (Budget room for students near RUPP, Backpacker room near Pub Street, Cosy room in Tuol Tom Poung (Occupied)). | Pass |  | screenshots/07_room_detail.png |  | QA Bot (Claude) | 2026-05-20

## Authentication
Module/Page | Feature | Test Scenario | Steps to Test | Expected Result | Actual Result | Status | Severity | Screenshot / Reference | Remark / Comment | Tested By | Testing Date
Authentication | AuthGuard redirect | Hitting /profile while logged out opens AuthModal | 1) Clear localStorage 'findroom.session' 2) Navigate to /profile | AuthGuard mounts AuthModal in Login mode; underlying page is gated behind backdrop. | AuthModal opened with 'Welcome back' heading, phone+password fields and 'No account yet? Create one' link. | Pass |  | screenshots/11_auth_modal_login.png |  | QA Bot (Claude) | 2026-05-20
Authentication | Login — empty submit | Submitting the login form with empty fields | 1) Click 'Log in' with no values entered | Native HTML5 'required' validation prevents submit and focuses the first empty field. | Browser focused the phone input; no request sent. | Pass |  | screenshots/11_auth_modal_login.png | Relies on native validation only — fine for current scope. | QA Bot (Claude) | 2026-05-20
Authentication | Login — phone format | Enter a phone with fewer than 8 digits | 1) Type '1234' in phone 2) Type 'somepass' in password 3) Click 'Log in' | Inline error: 'Enter a valid Cambodian phone number (8-9 digits after +855).' | Exact error message shown in red inline banner; submit blocked. | Pass |  | screenshots/12_auth_invalid_phone.png |  | QA Bot (Claude) | 2026-05-20
Authentication | Register — switch to signup | Click 'Create one' to switch tabs | 1) On login modal click 'Create one' | Modal switches to 'Create your account' with name + phone + password fields and 'At least 8 characters' password hint. | Modal swapped tabs as expected; placeholder hint visible. | Pass |  | screenshots/13_auth_register.png |  | QA Bot (Claude) | 2026-05-20
Authentication | Register — short password | Submit register with a 3-character password | 1) Name=QA Tester 2) Phone=87654321 3) Password=123 4) Click 'Create account' | Inline validation: 'Password must be at least 8 characters.' | Exact error displayed; account not created. | Pass |  | screenshots/14_auth_short_password.png |  | QA Bot (Claude) | 2026-05-20
Authentication | Register — successful signup | Submit register with valid credentials in demo mode | 1) Name=QA Tester 2) Phone=87654321 3) Password=password123 4) Click 'Create account' | Session created, modal closes, user lands on /profile with their entered username. | Session stored (uid demo-85587654321, username 'QA Tester'); however the profile header rendered the username from a previous demo user ('FindRoom user') with that user's avatar — see profile-overrides bug below. | Pass | High | screenshots/15_profile_after_register.png | FIXED 2026-05-20 — see linked fix below. Retested: new accounts now land on /profile with their own entered username and a clean (initial-only) avatar. | QA Bot (Claude) | 2026-05-20
Authentication | Profile overrides leak across users | A previous user's avatar and display name follow any new account on the same device | 1) Log in as user A and Edit Profile (change name + upload avatar) 2) Log out 3) Register or log in as user B 4) Visit /profile | Each session should see ONLY their own profile name and avatar. | localStorage 'findroom.profile-overrides' is stored under a single global key (not keyed by uid). Confirmed user B sees user A's saved username 'FindRoom user' and base64 cat avatar. | Pass | High | screenshots/16_overrides_leak.png | FIXED 2026-05-20 — src/lib/profile-overrides.ts now namespaces storage as findroom.profile-overrides.<uid>; legacy global key is purged on first load. Callers in profile/page.tsx, profile/list-room/page.tsx, components/Navbar.tsx updated to pass session.uid. Retested with two demo accounts: User B no longer inherits User A's name/avatar. | QA Bot (Claude) | 2026-05-20
Authentication | Log out | Log out from profile | 1) On /profile click 'Log out' | Session cleared, redirect to /explore, navbar shows 'Log in' instead of avatar. | Behaviour matches expectation (verified during session cleanup steps). | Pass |  |  |  | QA Bot (Claude) | 2026-05-20

## Profile Page
Module/Page | Feature | Test Scenario | Steps to Test | Expected Result | Actual Result | Status | Severity | Screenshot / Reference | Remark / Comment | Tested By | Testing Date
Profile Page | Empty listings state | Fresh user with no listings | 1) Clear local-rooms 2) Reload /profile | 'No listings yet' card with 'Create your first listing' CTA. | Empty state card with house icon, copy and CTA button shown. | Pass |  | screenshots/17_profile_empty.png |  | QA Bot (Claude) | 2026-05-20
Profile Page | Edit profile — save name | Update display name via Edit profile modal | 1) Click 'Edit profile' 2) Change Name to 'QA Tester Updated' 3) Click Save | Modal closes, header shows new name immediately. | Header updated to 'QA Tester Updated' without page reload. | Pass |  | screenshots/18_profile_edit_save.png |  | QA Bot (Claude) | 2026-05-20
Profile Page | Edit profile — modal copy | Edit profile modal copy & layout | 1) Open Edit profile modal | Modal contains Avatar uploader, Name (required), Login phone (required) with helper text about contacts. | All three controls present; helper text 'You sign in with this number. Changing it doesn't affect the contact info you publish on listings.' is helpful and clear. | Pass |  | screenshots/19_profile_edit_modal.png |  | QA Bot (Claude) | 2026-05-20
Profile Page | Listing action menu — Copy | Per-listing action menu duplicates a listing | 1) Click 3-dot 'Listing options' on a listing card 2) Click 'Copy' | Navigates to /profile/list-room?type=<type>&copyFrom=<id> with form pre-populated. | URL = /profile/list-room?type=apartment&copyFrom=local-1779243463762. Title field auto-filled with 'Copy of QA Test Apartment', description and other fields carried over. | Pass |  | screenshots/20_listing_copy.png | Photos correctly NOT copied (intended). | QA Bot (Claude) | 2026-05-20
Profile Page | Listing action menu — Mark as occupied / Delete | Menu exposes both actions | 1) Open per-listing 3-dot menu | Items 'Mark as occupied', 'Copy', 'Delete' visible. | All three items present in the floating menu (verified via DOM inspection). | Pass |  |  | End-to-end click of Mark/Delete not fully exercised due to menu being portalled outside the main tree — manual retest recommended. | QA Bot (Claude) | 2026-05-20

## List Room Form
Module/Page | Feature | Test Scenario | Steps to Test | Expected Result | Actual Result | Status | Severity | Screenshot / Reference | Remark / Comment | Tested By | Testing Date
List Room Form | Property type picker | Picker presents 6 property types when entering the form via CTA | 1) From profile, click 'List a room' / 'Create your first listing' | Modal lists Room, Apartment, Condo, Flat, House, Villa each with a one-line description. | All 6 options shown with subtitles. Clicking 'Apartment' navigates to /profile/list-room?type=apartment. | Pass |  | screenshots/21_listroom_typepicker.png |  | QA Bot (Claude) | 2026-05-20
List Room Form | Required field — Title | Submit the form with no title | 1) Open List Room form 2) Leave title empty 3) Click 'Publish listing' | Validation error appears under Title and form does not submit. | Inline message 'Add a title for your listing.' shown; submit blocked. | Pass |  | screenshots/22_listroom_title_required.png |  | QA Bot (Claude) | 2026-05-20
List Room Form | Required field — Province | Submit with title + description but no location | 1) Fill title + description 2) Click 'Publish listing' | Error: 'Pick a province for your listing.' | Exact message displayed. | Pass |  | screenshots/23_listroom_province_required.png |  | QA Bot (Claude) | 2026-05-20
List Room Form | Required field — Rent | Submit with title, description and province but no rent | 1) Set title, description, province=Phnom Penh / Chamkar Mon 2) Click 'Publish listing' | Error: 'Set a monthly rent amount.' | Exact message displayed. | Pass |  | screenshots/24_listroom_rent_required.png |  | QA Bot (Claude) | 2026-05-20
List Room Form | Successful publish | Submit fully valid listing | 1) Title='QA Test Apartment' 2) Description filled 3) Province=Phnom Penh / district=Chamkar Mon 4) Add fee, set Rent=$250 Monthly 5) Click 'Publish listing' | Form submits, user returns to /profile and new card appears under 'My listings'. | Redirected to /profile. 'QA Test Apartment' card with $250 / month, Chamkar Mon, Phnom Penh shown. Counter 'My listings 1'. | Pass |  | screenshots/25_listroom_publish_success.png | Listing also appears in /explore feed (merged with mock data). | QA Bot (Claude) | 2026-05-20
List Room Form | LocationPicker reused on listing form | 'Show all rooms in X' link appears inside the listing creation flow | 1) Open List Room form 2) Click 'Pick province' 3) Pick a province and district | Copy in the picker should match the context (e.g. 'Use this district' / 'Set district') rather than 'Show all rooms in X', which only makes sense on Explore. | Top of the picker still reads 'Show all rooms in Chamkar Mon'. Users on the listing form may be confused or click it expecting to back out. | Pass | Low | screenshots/26_listroom_picker_copy.png | FIXED 2026-05-20 — added `intent` prop to LocationPicker ('browse' default ¦ 'select'); list-room form passes intent='select'. Picker now reads 'Use Phnom Penh' / 'Use Chamkar Mon' / 'Clear' on the listing form. Retested. | QA Bot (Claude) | 2026-05-20
List Room Form | Mobile sticky footer | Mobile viewport shows Clear / Publish at the bottom | 1) Resize to 375x812 (mobile) 2) Open List Room form | Sticky footer with 'Clear' and 'Publish' buttons; BottomNav hidden on this route. | Sticky footer present, BottomNav correctly hidden on /profile/list-room. | Pass |  | screenshots/27_listroom_mobile_footer.png |  | QA Bot (Claude) | 2026-05-20

## Global Nav
Module/Page | Feature | Test Scenario | Steps to Test | Expected Result | Actual Result | Status | Severity | Screenshot / Reference | Remark / Comment | Tested By | Testing Date
Global Nav | Navbar — desktop | Desktop navbar exposes List room, language and avatar links | 1) Resize to 1280x820 2) Load /explore | Logo (left), 'List room' button, language flag toggle, and avatar/login slot (right). | Logo, 'List room' button, Cambodia flag toggle and 'Q' avatar shown. | Pass |  | screenshots/28_navbar_desktop.png |  | QA Bot (Claude) | 2026-05-20
Global Nav | BottomNav — mobile | BottomNav visible on listing/profile routes on mobile | 1) Resize to mobile preset 2) Visit /explore | Sticky bottom bar with Home, raised + FAB, Profile; safe-area padding for notched devices. | BottomNav with Home / + FAB / Profile rendered. Tapping + on a logged-out session triggers AuthModal (verified earlier). | Pass |  | screenshots/29_bottomnav_mobile.png | Correctly hidden on /profile/list-room and /rooms/[id]. | QA Bot (Claude) | 2026-05-20
Global Nav | Language toggle persistence | Toggle persists selected language across reloads | 1) Click language flag 2) Reload 3) Inspect localStorage 'findroom.language' and aria-label | Selection persists; aria-label and flag swap accordingly. | localStorage value flipped km <-> en; aria-label updated to 'Current language: English. Tap to switch to Khmer.' after reload. | Pass |  | screenshots/30_lang_toggle.png |  | QA Bot (Claude) | 2026-05-20
Global Nav | Language toggle — no UI translation | Switching language should translate UI strings | 1) Click language toggle to switch to km / en 2) Reload /explore and inspect headings | Visible copy (hero heading, search placeholders, etc.) should appear in the selected language. | All visible copy remained in English regardless of preference (km vs en). The toggle is a no-op for end users; only the stored preference changes. | Pass | Medium | screenshots_fixed/01_explore_km_desktop.png | FIXED 2026-05-20 — added in-file DICT + useT() hook in src/lib/language.ts; useLanguage now broadcasts a 'findroom:language-change' event so every consumer re-renders on toggle. New ExploreHero client component + SearchBar + ExploreRooms now translate hero, placeholders, type/sort labels, list/map tabs, and the rooms counter. Khmer translations need a native-speaker review before launch. | QA Bot (Claude) | 2026-05-20
Global Nav | Footer | Footer renders contact + meta info | 1) Scroll to footer on any page | Logo + blurb, 'GET IN TOUCH' (+855 12 345 678, Telegram, hello@findroom.kh, Facebook), copyright, 'Made in Cambodia'. | All four contact links + tagline + © 2026 FindRoom.KH + 'Made in Cambodia' visible. | Pass |  | screenshots/32_footer.png |  | QA Bot (Claude) | 2026-05-20

## Responsive Design
Module/Page | Feature | Test Scenario | Steps to Test | Expected Result | Actual Result | Status | Severity | Screenshot / Reference | Remark / Comment | Tested By | Testing Date
Responsive Design | Mobile (375x812) | Smoke check key pages at mobile width | 1) Resize to mobile preset 2) Browse /, /explore, /profile, /profile/list-room | Single-column layouts, BottomNav visible where appropriate, no horizontal scroll, sticky CTAs accessible. | Layouts collapse cleanly; BottomNav present on /explore and /profile; List Room sticky footer in place; no horizontal scroll detected. | Pass |  | screenshots/33_responsive_mobile.png |  | QA Bot (Claude) | 2026-05-20
Responsive Design | Tablet (768x1024) | Smoke check at tablet width | 1) Resize to tablet preset 2) Load /explore | Full desktop navbar visible, room grid 3 columns, search bar inputs readable. | Navbar full; grid 3 columns. However, search bar input labels truncate ('Where to? Pr…', 'Any Property …') because the bar width is tight. | Pass | Low | screenshots_fixed/02_explore_tablet_stacked.png | FIXED 2026-05-20 — switched SearchBar responsive breakpoints from sm: to lg: so the bar stacks vertically below 1024px. Each input gets full width on tablet and mobile, no truncation. Retested at 768x1024. | QA Bot (Claude) | 2026-05-20
Responsive Design | Desktop (1280x820) | Smoke check at desktop width | 1) Resize to desktop preset 2) Load /explore | Hero, full search bar, 4-column room grid, List/Map tabs aligned right. | All elements rendered as expected. | Pass |  | screenshots/01_explore_desktop.png |  | QA Bot (Claude) | 2026-05-20
Responsive Design | Mock data inconsistency — BKK1 in Chamkar Mon | Listing 'Bright shared room in BKK1' assigns area BKK1 to Chamkar Mon district | 1) Open /rooms/2 (or similar) 2) Note address 'St. 294, BKK1, Chamkar Mon, Phnom Penh' | BKK1 (Boeng Keng Kang 1) is currently part of the Boeng Keng Kang khan since the 2018 redistribution. | Mock data treats BKK1 as part of Chamkar Mon. May be intentional shorthand but the LocationPicker district list under Chamkar Mon does not include BKK1. | Pass | Low |  | FIXED 2026-05-20 — moved room id=2 in src/lib/mock-data.ts and the matching seed in src/lib/local-rooms.ts from district='Chamkar Mon' to district='Boeng Keng Kang' (area='Boeng Keng Kang Muoy'), matching the canonical structure in src/lib/locations.ts. Retested: filtering by Boeng Keng Kang now returns 'Bright shared room in BKK1' (was previously hidden under Chamkar Mon); filtering by Chamkar Mon no longer mis-attributes it. | QA Bot (Claude) | 2026-05-20

## All Cases
Module/Page | Feature | Test Scenario | Steps to Test | Expected Result | Actual Result | Status | Severity | Screenshot / Reference | Remark / Comment | Tested By | Testing Date
Explore Page | Initial render | Open /explore and verify hero, search, room grid render | 1) Navigate to http://localhost:3000/ 2) Page should redirect to /explore 3) Observe hero, search bar and listing grid | Hero heading, sub-tagline, 3-input search bar, List/Map tabs and room cards visible. Counter shows 'N rooms available right now'. | Hero, search bar (Where to / Property type / Sort by price + Search button), List/Map tabs and 29 mock listings rendered. Counter reads '29 rooms available right now'. | Pass |  | screenshots/01_explore_desktop.png | Page redirect from / to /explore works. | QA Bot (Claude) | 2026-05-20
Explore Page | Location filter (province) | Cascading location picker filters listings | 1) Click 'Where to?' button 2) Pick 'Phnom Penh' -> 'Chamkar Mon' 3) Click 'Show all rooms in Chamkar Mon' | Listing count updates to only listings in selected district; chip pill shows 'Phnom Penh, Chamkar Mon' with clear (×) affordance. | Counter dropped from 29 to 6 rooms. Selected chip with × button rendered correctly. | Pass |  | screenshots/02_explore_filter_chamkar_mon.png |  | QA Bot (Claude) | 2026-05-20
Explore Page | Property type filter | Selecting a property type narrows results | 1) Open 'Any Property Type' dropdown 2) Pick 'Room' | Counter reflects rooms-only count; pluralisation correct. | After picking Room (with Chamkar Mon still set) counter read '1 room available right now'. Singular form correct. | Pass |  | screenshots/03_explore_filter_room.png |  | QA Bot (Claude) | 2026-05-20
Explore Page | Sort by price | Sort order applies to current filtered set | 1) Open 'Sort by price' dropdown 2) Select 'Price: low to high' | Cards reorder by price ascending; selected label persists on the button. | Sort options dropdown opened with three choices, low-to-high applied and label updated on the button. | Pass |  | screenshots/04_explore_sort.png |  | QA Bot (Claude) | 2026-05-20
Explore Page | Clear location chip | × on selected chip removes that filter | 1) With Phnom Penh / Chamkar Mon set, click × on the chip | Location filter cleared, other filters (type, sort) remain. | Location cleared, counter returned to 3 rooms (Room type still active). Other filters preserved as expected. | Pass |  | screenshots/05_explore_clear_location.png |  | QA Bot (Claude) | 2026-05-20
Explore Page | Map view tab | Switch from list to map view | 1) Click 'Map' tab | List replaced by interactive Leaflet map; counter switches phrasing to 'N rooms in this area'. | Leaflet map rendered with tiles, counter changed to '1 room in this area'. | Pass |  | screenshots/06_explore_map.png | Counter phrasing differs (in this area vs available right now); this is by design but worth a doc note. | QA Bot (Claude) | 2026-05-20
Room Detail | Page render | /rooms/2 displays hero, stats, description, fees and host card | 1) From explore click a room card 2) Verify hero image, title, address, $price, bedrooms/area/floor stats, description, amenities and fees table | All sections render; Back link visible; sidebar shows host card and location card. | Hero image with property type badge, title 'Bright shared room in BKK1', address, price $180/month, stats (1 Bed / 18m² / 2 Floor), 'About this place', 'What this place offers' (4 amenities), Fees & utilities table (rent / deposit / electricity / water) and host card with phone + Telegram all rendered. | Pass |  | screenshots/07_room_detail.png |  | QA Bot (Claude) | 2026-05-20
Room Detail | Image gallery (lightbox) | '3 photos' button opens full-screen viewer | 1) Click the '3 photos' button on the hero | Full-screen viewer covers viewport, shows all photos with thumbnails; Esc / close button dismisses. | Lightbox opens, but photos render as a tiled grid that does NOT fill the viewport — large empty area visible and the page header bleeds through behind the overlay. | Pass | Low | screenshots_fixed/03_room_detail.png | FIXED 2026-05-20 — rewrote viewer in src/components/ImageGallery.tsx as a single-image carousel with prev/next chevrons + thumbnail strip; backdrop changed from bg-ink/95 to bg-ink (fully opaque). Retested: lightbox now covers viewport completely. | QA Bot (Claude) | 2026-05-20
Room Detail | Phone & Telegram links | Host contact links open native handlers | 1) Inspect <a href> on host card | Phone link uses tel:+855... and Telegram link uses https://t.me/+855... | Phone href = tel:+85517888112; Telegram href = https://t.me/+85517888112. Both formats correct. | Pass |  | screenshots/07_room_detail.png |  | QA Bot (Claude) | 2026-05-20
Room Detail | Deferred Google Maps embed | 'Show map' lazy-loads Google Maps iframe | 1) Scroll to Location card 2) Click 'Show map' | Iframe loads with src pointing at google.com/maps?q=lat,lng | Iframe injected with src=https://www.google.com/maps?q=11.5444%2C104.9263&z=15&output=embed | Pass |  | screenshots/09_room_show_map.png | Lazy load avoids loading Maps on initial paint — good for performance. | QA Bot (Claude) | 2026-05-20
Room Detail | Missing room fallback | Visit /rooms/9999 (non-existent id) | 1) Navigate to /rooms/9999 | Friendly empty state with 'Back to Explore' CTA. | 'Room not found' heading, supporting copy and 'Back to Explore' button rendered correctly. | Pass |  | screenshots/10_room_not_found.png |  | QA Bot (Claude) | 2026-05-20
Room Detail | Similar rooms | Bottom section shows up to 3 similar listings | 1) Scroll to the bottom of /rooms/2 | 3 'Similar rooms' cards each linking to its own detail page. | 3 cards rendered (Budget room for students near RUPP, Backpacker room near Pub Street, Cosy room in Tuol Tom Poung (Occupied)). | Pass |  | screenshots/07_room_detail.png |  | QA Bot (Claude) | 2026-05-20
Authentication | AuthGuard redirect | Hitting /profile while logged out opens AuthModal | 1) Clear localStorage 'findroom.session' 2) Navigate to /profile | AuthGuard mounts AuthModal in Login mode; underlying page is gated behind backdrop. | AuthModal opened with 'Welcome back' heading, phone+password fields and 'No account yet? Create one' link. | Pass |  | screenshots/11_auth_modal_login.png |  | QA Bot (Claude) | 2026-05-20
Authentication | Login — empty submit | Submitting the login form with empty fields | 1) Click 'Log in' with no values entered | Native HTML5 'required' validation prevents submit and focuses the first empty field. | Browser focused the phone input; no request sent. | Pass |  | screenshots/11_auth_modal_login.png | Relies on native validation only — fine for current scope. | QA Bot (Claude) | 2026-05-20
Authentication | Login — phone format | Enter a phone with fewer than 8 digits | 1) Type '1234' in phone 2) Type 'somepass' in password 3) Click 'Log in' | Inline error: 'Enter a valid Cambodian phone number (8-9 digits after +855).' | Exact error message shown in red inline banner; submit blocked. | Pass |  | screenshots/12_auth_invalid_phone.png |  | QA Bot (Claude) | 2026-05-20
Authentication | Register — switch to signup | Click 'Create one' to switch tabs | 1) On login modal click 'Create one' | Modal switches to 'Create your account' with name + phone + password fields and 'At least 8 characters' password hint. | Modal swapped tabs as expected; placeholder hint visible. | Pass |  | screenshots/13_auth_register.png |  | QA Bot (Claude) | 2026-05-20
Authentication | Register — short password | Submit register with a 3-character password | 1) Name=QA Tester 2) Phone=87654321 3) Password=123 4) Click 'Create account' | Inline validation: 'Password must be at least 8 characters.' | Exact error displayed; account not created. | Pass |  | screenshots/14_auth_short_password.png |  | QA Bot (Claude) | 2026-05-20
Authentication | Register — successful signup | Submit register with valid credentials in demo mode | 1) Name=QA Tester 2) Phone=87654321 3) Password=password123 4) Click 'Create account' | Session created, modal closes, user lands on /profile with their entered username. | Session stored (uid demo-85587654321, username 'QA Tester'); however the profile header rendered the username from a previous demo user ('FindRoom user') with that user's avatar — see profile-overrides bug below. | Pass | High | screenshots/15_profile_after_register.png | FIXED 2026-05-20 — see linked fix below. Retested: new accounts now land on /profile with their own entered username and a clean (initial-only) avatar. | QA Bot (Claude) | 2026-05-20
Authentication | Profile overrides leak across users | A previous user's avatar and display name follow any new account on the same device | 1) Log in as user A and Edit Profile (change name + upload avatar) 2) Log out 3) Register or log in as user B 4) Visit /profile | Each session should see ONLY their own profile name and avatar. | localStorage 'findroom.profile-overrides' is stored under a single global key (not keyed by uid). Confirmed user B sees user A's saved username 'FindRoom user' and base64 cat avatar. | Pass | High | screenshots/16_overrides_leak.png | FIXED 2026-05-20 — src/lib/profile-overrides.ts now namespaces storage as findroom.profile-overrides.<uid>; legacy global key is purged on first load. Callers in profile/page.tsx, profile/list-room/page.tsx, components/Navbar.tsx updated to pass session.uid. Retested with two demo accounts: User B no longer inherits User A's name/avatar. | QA Bot (Claude) | 2026-05-20
Authentication | Log out | Log out from profile | 1) On /profile click 'Log out' | Session cleared, redirect to /explore, navbar shows 'Log in' instead of avatar. | Behaviour matches expectation (verified during session cleanup steps). | Pass |  |  |  | QA Bot (Claude) | 2026-05-20
Profile Page | Empty listings state | Fresh user with no listings | 1) Clear local-rooms 2) Reload /profile | 'No listings yet' card with 'Create your first listing' CTA. | Empty state card with house icon, copy and CTA button shown. | Pass |  | screenshots/17_profile_empty.png |  | QA Bot (Claude) | 2026-05-20
Profile Page | Edit profile — save name | Update display name via Edit profile modal | 1) Click 'Edit profile' 2) Change Name to 'QA Tester Updated' 3) Click Save | Modal closes, header shows new name immediately. | Header updated to 'QA Tester Updated' without page reload. | Pass |  | screenshots/18_profile_edit_save.png |  | QA Bot (Claude) | 2026-05-20
Profile Page | Edit profile — modal copy | Edit profile modal copy & layout | 1) Open Edit profile modal | Modal contains Avatar uploader, Name (required), Login phone (required) with helper text about contacts. | All three controls present; helper text 'You sign in with this number. Changing it doesn't affect the contact info you publish on listings.' is helpful and clear. | Pass |  | screenshots/19_profile_edit_modal.png |  | QA Bot (Claude) | 2026-05-20
Profile Page | Listing action menu — Copy | Per-listing action menu duplicates a listing | 1) Click 3-dot 'Listing options' on a listing card 2) Click 'Copy' | Navigates to /profile/list-room?type=<type>&copyFrom=<id> with form pre-populated. | URL = /profile/list-room?type=apartment&copyFrom=local-1779243463762. Title field auto-filled with 'Copy of QA Test Apartment', description and other fields carried over. | Pass |  | screenshots/20_listing_copy.png | Photos correctly NOT copied (intended). | QA Bot (Claude) | 2026-05-20
Profile Page | Listing action menu — Mark as occupied / Delete | Menu exposes both actions | 1) Open per-listing 3-dot menu | Items 'Mark as occupied', 'Copy', 'Delete' visible. | All three items present in the floating menu (verified via DOM inspection). | Pass |  |  | End-to-end click of Mark/Delete not fully exercised due to menu being portalled outside the main tree — manual retest recommended. | QA Bot (Claude) | 2026-05-20
List Room Form | Property type picker | Picker presents 6 property types when entering the form via CTA | 1) From profile, click 'List a room' / 'Create your first listing' | Modal lists Room, Apartment, Condo, Flat, House, Villa each with a one-line description. | All 6 options shown with subtitles. Clicking 'Apartment' navigates to /profile/list-room?type=apartment. | Pass |  | screenshots/21_listroom_typepicker.png |  | QA Bot (Claude) | 2026-05-20
List Room Form | Required field — Title | Submit the form with no title | 1) Open List Room form 2) Leave title empty 3) Click 'Publish listing' | Validation error appears under Title and form does not submit. | Inline message 'Add a title for your listing.' shown; submit blocked. | Pass |  | screenshots/22_listroom_title_required.png |  | QA Bot (Claude) | 2026-05-20
List Room Form | Required field — Province | Submit with title + description but no location | 1) Fill title + description 2) Click 'Publish listing' | Error: 'Pick a province for your listing.' | Exact message displayed. | Pass |  | screenshots/23_listroom_province_required.png |  | QA Bot (Claude) | 2026-05-20
List Room Form | Required field — Rent | Submit with title, description and province but no rent | 1) Set title, description, province=Phnom Penh / Chamkar Mon 2) Click 'Publish listing' | Error: 'Set a monthly rent amount.' | Exact message displayed. | Pass |  | screenshots/24_listroom_rent_required.png |  | QA Bot (Claude) | 2026-05-20
List Room Form | Successful publish | Submit fully valid listing | 1) Title='QA Test Apartment' 2) Description filled 3) Province=Phnom Penh / district=Chamkar Mon 4) Add fee, set Rent=$250 Monthly 5) Click 'Publish listing' | Form submits, user returns to /profile and new card appears under 'My listings'. | Redirected to /profile. 'QA Test Apartment' card with $250 / month, Chamkar Mon, Phnom Penh shown. Counter 'My listings 1'. | Pass |  | screenshots/25_listroom_publish_success.png | Listing also appears in /explore feed (merged with mock data). | QA Bot (Claude) | 2026-05-20
List Room Form | LocationPicker reused on listing form | 'Show all rooms in X' link appears inside the listing creation flow | 1) Open List Room form 2) Click 'Pick province' 3) Pick a province and district | Copy in the picker should match the context (e.g. 'Use this district' / 'Set district') rather than 'Show all rooms in X', which only makes sense on Explore. | Top of the picker still reads 'Show all rooms in Chamkar Mon'. Users on the listing form may be confused or click it expecting to back out. | Pass | Low | screenshots/26_listroom_picker_copy.png | FIXED 2026-05-20 — added `intent` prop to LocationPicker ('browse' default ¦ 'select'); list-room form passes intent='select'. Picker now reads 'Use Phnom Penh' / 'Use Chamkar Mon' / 'Clear' on the listing form. Retested. | QA Bot (Claude) | 2026-05-20
List Room Form | Mobile sticky footer | Mobile viewport shows Clear / Publish at the bottom | 1) Resize to 375x812 (mobile) 2) Open List Room form | Sticky footer with 'Clear' and 'Publish' buttons; BottomNav hidden on this route. | Sticky footer present, BottomNav correctly hidden on /profile/list-room. | Pass |  | screenshots/27_listroom_mobile_footer.png |  | QA Bot (Claude) | 2026-05-20
Global Nav | Navbar — desktop | Desktop navbar exposes List room, language and avatar links | 1) Resize to 1280x820 2) Load /explore | Logo (left), 'List room' button, language flag toggle, and avatar/login slot (right). | Logo, 'List room' button, Cambodia flag toggle and 'Q' avatar shown. | Pass |  | screenshots/28_navbar_desktop.png |  | QA Bot (Claude) | 2026-05-20
Global Nav | BottomNav — mobile | BottomNav visible on listing/profile routes on mobile | 1) Resize to mobile preset 2) Visit /explore | Sticky bottom bar with Home, raised + FAB, Profile; safe-area padding for notched devices. | BottomNav with Home / + FAB / Profile rendered. Tapping + on a logged-out session triggers AuthModal (verified earlier). | Pass |  | screenshots/29_bottomnav_mobile.png | Correctly hidden on /profile/list-room and /rooms/[id]. | QA Bot (Claude) | 2026-05-20
Global Nav | Language toggle persistence | Toggle persists selected language across reloads | 1) Click language flag 2) Reload 3) Inspect localStorage 'findroom.language' and aria-label | Selection persists; aria-label and flag swap accordingly. | localStorage value flipped km <-> en; aria-label updated to 'Current language: English. Tap to switch to Khmer.' after reload. | Pass |  | screenshots/30_lang_toggle.png |  | QA Bot (Claude) | 2026-05-20
Global Nav | Language toggle — no UI translation | Switching language should translate UI strings | 1) Click language toggle to switch to km / en 2) Reload /explore and inspect headings | Visible copy (hero heading, search placeholders, etc.) should appear in the selected language. | All visible copy remained in English regardless of preference (km vs en). The toggle is a no-op for end users; only the stored preference changes. | Pass | Medium | screenshots_fixed/01_explore_km_desktop.png | FIXED 2026-05-20 — added in-file DICT + useT() hook in src/lib/language.ts; useLanguage now broadcasts a 'findroom:language-change' event so every consumer re-renders on toggle. New ExploreHero client component + SearchBar + ExploreRooms now translate hero, placeholders, type/sort labels, list/map tabs, and the rooms counter. Khmer translations need a native-speaker review before launch. | QA Bot (Claude) | 2026-05-20
Global Nav | Footer | Footer renders contact + meta info | 1) Scroll to footer on any page | Logo + blurb, 'GET IN TOUCH' (+855 12 345 678, Telegram, hello@findroom.kh, Facebook), copyright, 'Made in Cambodia'. | All four contact links + tagline + © 2026 FindRoom.KH + 'Made in Cambodia' visible. | Pass |  | screenshots/32_footer.png |  | QA Bot (Claude) | 2026-05-20
Responsive Design | Mobile (375x812) | Smoke check key pages at mobile width | 1) Resize to mobile preset 2) Browse /, /explore, /profile, /profile/list-room | Single-column layouts, BottomNav visible where appropriate, no horizontal scroll, sticky CTAs accessible. | Layouts collapse cleanly; BottomNav present on /explore and /profile; List Room sticky footer in place; no horizontal scroll detected. | Pass |  | screenshots/33_responsive_mobile.png |  | QA Bot (Claude) | 2026-05-20
Responsive Design | Tablet (768x1024) | Smoke check at tablet width | 1) Resize to tablet preset 2) Load /explore | Full desktop navbar visible, room grid 3 columns, search bar inputs readable. | Navbar full; grid 3 columns. However, search bar input labels truncate ('Where to? Pr…', 'Any Property …') because the bar width is tight. | Pass | Low | screenshots_fixed/02_explore_tablet_stacked.png | FIXED 2026-05-20 — switched SearchBar responsive breakpoints from sm: to lg: so the bar stacks vertically below 1024px. Each input gets full width on tablet and mobile, no truncation. Retested at 768x1024. | QA Bot (Claude) | 2026-05-20
Responsive Design | Desktop (1280x820) | Smoke check at desktop width | 1) Resize to desktop preset 2) Load /explore | Hero, full search bar, 4-column room grid, List/Map tabs aligned right. | All elements rendered as expected. | Pass |  | screenshots/01_explore_desktop.png |  | QA Bot (Claude) | 2026-05-20
Responsive Design | Mock data inconsistency — BKK1 in Chamkar Mon | Listing 'Bright shared room in BKK1' assigns area BKK1 to Chamkar Mon district | 1) Open /rooms/2 (or similar) 2) Note address 'St. 294, BKK1, Chamkar Mon, Phnom Penh' | BKK1 (Boeng Keng Kang 1) is currently part of the Boeng Keng Kang khan since the 2018 redistribution. | Mock data treats BKK1 as part of Chamkar Mon. May be intentional shorthand but the LocationPicker district list under Chamkar Mon does not include BKK1. | Pass | Low |  | FIXED 2026-05-20 — moved room id=2 in src/lib/mock-data.ts and the matching seed in src/lib/local-rooms.ts from district='Chamkar Mon' to district='Boeng Keng Kang' (area='Boeng Keng Kang Muoy'), matching the canonical structure in src/lib/locations.ts. Retested: filtering by Boeng Keng Kang now returns 'Bright shared room in BKK1' (was previously hidden under Chamkar Mon); filtering by Chamkar Mon no longer mis-attributes it. | QA Bot (Claude) | 2026-05-20