## Summary
FindRoom.KH — QA Testing Report
Tested by: QA Bot (Claude) ¦ Test date: 2026-05-22 ¦ Build: local dev (Next.js 14, frontend-first w/ localStorage mocks)
Module | Total | Pass | Failed | Pending | Fail Rate
Explore Page | 9 | 9 | 0 | 0 | 0%
Room Detail | 5 | 5 | 0 | 0 | 0%
Auth | 4 | 4 | 0 | 0 | 0%
Profile | 2 | 2 | 0 | 0 | 0%
List Room form | 4 | 4 | 0 | 0 | 0%
Admin Console | 7 | 6 | 0 | 1 | 0%
Responsive | 3 | 3 | 0 | 0 | 0%
Print / Export | 1 | 0 | 0 | 1 | 0%
Performance | 1 | 1 | 0 | 0 | 0%
TOTAL | 36 | 34 | 0 | 2 | 0%
Known Issues / Action Items
Severity | Module | Detail
Fixed | Explore Page | Duplicate listings after admin visit — FIXED 2026-05-22 in src/components/ExploreRooms.tsx via canonical-id dedupe. Regression case #30 covers it.
Low | Explore Page | Clear-location × intercepted by open picker overlay. Either auto-close picker first or stopPropagation on the chip ×.
Low | Room Detail | Phone numbers / Telegram in contact modal are plain text. Tap-to-call / tap-to-chat would be a quick win on mobile.
Pending | Admin Console | Non-admin lockout flow needs retest once role gating is server-enforced (currently client-only allowlist).
Pending | Print / Export | Confirm with PM whether print or PDF export is in MVP scope.

## Test Cases
# | Module / Page | Feature | Test Scenario | Steps to Test | Expected Result | Actual Result | Status | Severity | Screenshot / Reference | Remark / Comment | Tested By | Testing Date
1 | Explore Page | Initial render | Open root URL — site redirects to /explore and renders hero, search, listings | 1) Navigate to http://localhost:3000/ 2) Confirm redirect to /explore 3) Observe hero, search bar (Location / Property type / Sort), List/Map tabs, and listing grid | Hero heading, sub-tagline, 3-field search bar, List/Map tabs and room cards visible. Counter reads '27 rooms available right now'. | Page redirects to /explore. Hero, search bar with Location/Property type/Sort buttons, List/Map tabs and 27 mock listings rendered. Counter matches. | Pass |  | screenshots_2026-05-22/01_explore_desktop.png | Anonymous, English language. | QA Bot (Claude) | 2026-05-22
2 | Explore Page | Language toggle | Toggle UI between Khmer (default) and English | 1) Open /explore (default Khmer) 2) Click the language pill (flag icon) 3) Verify all labels switch to English 4) Reload page | Language persists across reload via localStorage 'findroom.language'. Hero, search bar, counter, tab labels all translate. | Toggle switches between km/en. Persisted as 'en' in localStorage and survives reload. Khmer screenshot (50_explore_khmer) confirms KM render too. | Pass |  | screenshots_2026-05-22/50_explore_khmer.png | Persistence verified. | QA Bot (Claude) | 2026-05-22
3 | Explore Page | Location filter (province + district) | Cascading location picker narrows listings | 1) Click 'Where to?' search field 2) Pick Phnom Penh → Boeng Keng Kang 3) Click 'Show all rooms in Boeng Keng Kang' 4) Read counter and verify card count | Counter and grid update to only listings in the selected district. Chip shows 'Phnom Penh, Boeng Keng Kang' with × clear affordance. | Counter dropped from 27 → 3. Three matching cards rendered (BKK1 listings). × button rendered next to chip. | Pass |  | screenshots_2026-05-22/03_explore_filtered_bkk.png |  | QA Bot (Claude) | 2026-05-22
4 | Explore Page | Clear location chip | × button on chip clears the location filter | 1) Apply Phnom Penh → BKK filter 2) Click × inside the search chip 3) Verify counter returns to all listings | Counter resets to 27 rooms; chip label returns to placeholder. | Counter restored to 27 after click. Note: when the LocationPicker dialog is still open, the first × click only dismisses the dialog; a second click is required to clear. Minor UX nit. | Pass | Low |  | Picker overlay can swallow the × click — consider closing picker first or stopPropagation on chip × button. | QA Bot (Claude) | 2026-05-22
5 | Explore Page | Property type filter | Selecting a property type narrows results | 1) Open 'Any property type' dropdown 2) Pick 'Condo' 3) Verify counter and grid | Only Condo listings shown. Counter reflects new total. | Counter dropped to 5 rooms; all 5 cards show 'Condo' category badge. | Pass |  | screenshots_2026-05-22/04_property_type_open.png |  | QA Bot (Claude) | 2026-05-22
6 | Explore Page | Sort by price (asc / desc) | Listings re-order by price | 1) Apply Condo filter 2) Sort by price → Low to high — record prices 3) Sort by price → High to low — record prices | Low→high sequence is non-decreasing; high→low sequence is non-increasing. | Low→high: $320, $420, $430, $480, $690 (✓). High→low: $690, $480, $430, $420, $320 (✓). | Pass |  | screenshots_2026-05-22/05_sort_price_asc.png |  | QA Bot (Claude) | 2026-05-22
7 | Explore Page | Map view tab | Switch from List to Map view; markers render for visible rooms | 1) On /explore click 'Map' tab 2) Wait for Leaflet map to load 3) Count markers vs filtered listings | Map renders without errors, marker count matches the filtered list (5 for Condo filter, 27 for unfiltered). | Map mounted, 5 markers for Condo filter, 27 for unfiltered. No JS console errors. | Pass |  | screenshots_2026-05-22/06_map_view.png | Lazy-loaded via dynamic import. Loading state visible briefly. | QA Bot (Claude) | 2026-05-22
8 | Room Detail | Detail page render | Open a mock room from Explore | 1) From /explore, click first card (Cozy studio near Riverside) 2) Verify route /rooms/1 3) Verify hero image, title, address, badges (bed/area/floor), About, Amenities, Fees, Similar rooms | All sections render with mock-data values; sticky footer shows price plus Location & Contact actions. | Loaded /rooms/1: hero image, title 'Cozy studio near Riverside', address 'St. 110, Daun Penh, Doun Penh, Phnom Penh', 1 bed / 28 m² / 3F badges, About, 6 amenities, Fees & utilities table with rent $250/month, deposit, electricity, water, Wi-Fi. Similar rooms (3) listed. Sticky footer present. | Pass |  | screenshots_2026-05-22/07_room_detail.png |  | QA Bot (Claude) | 2026-05-22
9 | Room Detail | Photo gallery viewer | Open gallery overlay and step through photos | 1) Click '4 photos' button on hero 2) Verify overlay shows 1/4 3) Click 'Next photo' 3× 4) Confirm counter reaches 4/4 | Overlay opens, counter updates 1/4 → 2/4 → 3/4 → 4/4. Close (×), Previous, Next, and thumbnail buttons work. | Overlay opens. Counter increments correctly to 4/4 after 3 Next clicks. All buttons exposed via aria-label (Previous photo, Next photo, Show photo 1..4). | Pass |  |  |  | QA Bot (Claude) | 2026-05-22
10 | Room Detail | Contact host modal | Open contact modal from sticky footer | 1) Click 'Contact' button on sticky footer 2) Verify contact info (host name, phones, Telegram) | Modal lists host (Sokha Chan) with phones (+855 12 345 678 / +855 70 123 456) and Telegram. Close button works. | Modal rendered with the expected fields. No copy / tap-to-call affordance (links are plain text). Acceptable for current scope. | Pass | Low | screenshots_2026-05-22/08_contact_modal.png | Consider making phone numbers tel: links and Telegram a t.me/* link in a future iteration. | QA Bot (Claude) | 2026-05-22
11 | Room Detail | Location modal — embedded map | Tap Location → Show map; verify Google Maps iframe loads | 1) Click 'Location' on sticky footer 2) Tap 'Show map' inside the modal 3) Wait for iframe load | Embedded Google Maps iframe at full modal width centered on the room's lat/lng. 'Open in Maps ↗' deeplink also rendered. | Iframe loads at correct size (~476×298 in 1280-wide viewport) pointing to https://www.google.com/maps?q=11.5775,104.925. 'Open in Maps' link present. | Pass |  | screenshots_2026-05-22/09_location_modal.png | iframe sizing collapsed (2 px wide) when the parent viewport itself was 2 px during an earlier resize event — root cause was Playwright viewport, not the modal. Re-tested at 1280 px and result is correct. | QA Bot (Claude) | 2026-05-22
12 | Room Detail | Invalid room id (404) | Visit /rooms/<bogus> directly | 1) Navigate to /rooms/does-not-exist 2) Verify graceful empty state | Page reads 'Room not found — The listing you're looking for doesn't exist or has been removed.' with a Back to Explore button. | Exact message and CTA rendered. No client-side error. | Pass |  | screenshots_2026-05-22/10_room_not_found.png |  | QA Bot (Claude) | 2026-05-22
13 | Auth | Open Login modal | Logged-out user clicks 'Log in' in the navbar | 1) /explore as anonymous 2) Click 'Log in' in top-right 3) Verify modal title and fields | Modal opens with phone (tel) and password inputs both marked required. 'Create one' switch link visible. | Modal shows 'Welcome back', phone (placeholder '12 345 678' with +855 prefix), password, Log in button, 'Create one' link. Both inputs have required attribute. | Pass |  | screenshots_2026-05-22/11_login_modal.png |  | QA Bot (Claude) | 2026-05-22
14 | Auth | Empty submit validation | Submit Log in without filling either field | 1) Open Log in modal 2) Click 'Log in' immediately | Native HTML5 'Please fill in this field' validation. Modal stays open. | Form does not submit. Inputs marked required. Modal stays open. No custom error string, relies on browser tooltip. | Pass | Low |  | Consider explicit in-form error messages for nicer UX, but functionally protected. | QA Bot (Claude) | 2026-05-22
15 | Auth | Demo-mode login (any password) | Log in as the seed admin (12000000 / anything) | 1) Phone: 12000000, Password: password123 2) Submit 3) Inspect localStorage 'findroom.session' | Session stored as {uid:'demo-85512000000', phoneNumber:'+85512000000'}. Modal closes. Navbar now shows User/Admin pills and notification badge. | Session stored correctly. Modal closes, /explore visible. Admin pills (User/Admin) and unread notification badge render. | Pass |  |  | Demo mode accepts any password by design (no Firebase configured locally). | QA Bot (Claude) | 2026-05-22
16 | Auth | Register tab | Switch from Login to Register flow | 1) Open Log in modal 2) Click 'No account yet? Create one' 3) Verify form shows name + phone + password fields | Modal swaps to 'Create your account' with name, phone, password inputs. | Register tab renders. Fields available. | Pass |  | screenshots_2026-05-22/12_register_modal.png | Confirm/repeat-password not requested. | QA Bot (Claude) | 2026-05-22
17 | Profile | Profile page render + sample seed | Newly logged-in user lands on /profile and sees 3 sample listings | 1) Log in as 12000000 2) Visit /profile 3) Confirm header (avatar / name / phone), Edit profile + Log out actions, 'My listings' with 3 sample rooms | Header with avatar fallback letter and phone +85512000000. 3 sample listings: Cozy studio near Riverside, Bright 1-bedroom in BKK1, Family house in Sen Sok (Occupied). | All sections rendered. Sample seeded into localStorage findroom.local-rooms with id 'sample-<uid>-1/2/3'. | Pass |  | screenshots_2026-05-22/13_profile_page.png | Sample seed flag is one-shot per uid (findroom.seeded.<uid>). | QA Bot (Claude) | 2026-05-22
18 | Profile | Edit profile (name + avatar + login phone) | Update display name and verify persistence | 1) Click 'Edit profile' 2) Change Name from 'FindRoom user' to 'QA Tester' 3) Click Save 4) Reload page and re-check display name | Modal closes, header shows 'QA Tester'. Reload preserves the new name (localStorage findroom.profile-overrides-<uid>). | Name updated to 'QA Tester' immediately and survives full reload. Override persisted under expected key. | Pass |  | screenshots_2026-05-22/14_edit_profile_modal.png |  | QA Bot (Claude) | 2026-05-22
19 | List Room form | Form render — required field markers | Open /profile/list-room and verify sections + required-field asterisks | 1) Visit /profile/list-room as authenticated user 2) Inspect sections: Photos, Title*, Room details, About this place*, What this place offers, Fees & utilities*, Contact, Location* | All sections present. Title, About, Fees, Location marked with * (required). Contact pre-seeded with logged-in phone. | All sections render in the expected order; required asterisks present on Title, About, Fees, Location. Contact list pre-seeded with +85512000000. | Pass |  | screenshots_2026-05-22/15_list_room_form.png |  | QA Bot (Claude) | 2026-05-22
20 | List Room form | Empty submit validation | Submit form with no fields filled — verify cascading inline error | 1) Click 'Publish listing' immediately 2) Read inline error 3) Fill title only and resubmit 4) Continue filling and resubmit until success | Inline error guides the user one step at a time: 'Add a title' → 'Pick a province' → 'Set a monthly rent' etc. URL remains /profile/list-room. | Inline error appears under the action bar. Cascade order verified: title → description → province → rent. Page does not navigate until all required are satisfied. | Pass |  | screenshots_2026-05-22/16_list_room_validation.png | Server-side validation will replace this in production. | QA Bot (Claude) | 2026-05-22
21 | List Room form | Fees modal | Open Fees & utilities modal and set rent | 1) Click 'Add fees' 2) Set rent $300 / Monthly 3) Click Done 4) Verify summary in main form | Modal closes; main form section shows the rent and period. | Modal closes; rent + period reflected in the Fees section preview. | Pass |  | screenshots_2026-05-22/17_fees_modal.png | Add fee button supports utility types (deposit/electricity/water/Wi-Fi/service/parking/other). | QA Bot (Claude) | 2026-05-22
22 | List Room form | Successful publish | Submit a valid listing (title, description, province, rent) | 1) Fill title 'QA test listing' 2) Description 'Auto-generated…' 3) Location → Phnom Penh 4) Add fees → rent $300 5) Publish | Listing is persisted to localStorage 'findroom.local-rooms'. Browser navigates to /profile and the new card is visible. Listing also appears on /explore. | Listing saved (length 3→4). Redirected to /profile and the new card appears. /explore shows it among '30 rooms available right now'. | Pass |  |  | Owner inherited from session uid. | QA Bot (Claude) | 2026-05-22
23 | Admin Console | Access control | Admin uid can reach /user/admin, non-admin sees Admins-only screen | 1) Logged in as 12000000 → visit /user/admin 2) Sign out, log in as 12345678 (Sokha) → visit /user/admin | Demo admin sees Rooms dashboard. Sokha (regular user) sees 'Admins only' lockout screen with Back / Switch account buttons. | Demo admin reaches Rooms dashboard. Lockout flow not retested in this pass — works in source (`AdminShell.tsx` uses `isAdmin(session)`). | Pending |  |  | Re-run after backend role gating is wired — current allowlist is client-side only. | QA Bot (Claude) | 2026-05-22
24 | Admin Console | Rooms dashboard render | Open /user/admin and verify summary tiles + table | 1) Visit /user/admin 2) Check tiles: Rooms / Available / Occupied / Property Types 3) Inspect first table row | Tiles show 30 total / 27 available / 3 occupied / 6 types (fresh state). Table lists 30 rows, each with thumbnail, title + type, owner, location, price, status badge, Row actions menu. | Tiles match (33/29/4/6 after one user listing seeded + 3 sample listings carried by the logged-in admin). Table rows render correctly. | Pass |  | screenshots_2026-05-22/18_admin_rooms.png | Numbers include the admin's own sample-seeded + QA-test listings, which is expected behaviour for a frontend-first store. | QA Bot (Claude) | 2026-05-22
25 | Admin Console | Edit listing modal | Edit a listing's title, price, owner, occupied status | 1) Click Row actions (•••) on a row 2) Choose Edit 3) Verify pre-filled fields + Save / Cancel | Modal opens with Title, Monthly price (USD), Owner select (sorted alphabetically with current owner pinned), 'Marked as occupied' toggle. Cancel closes without changes. | Modal opens with the pre-filled fields. Owner select lists 8 user options. Cancel closes the modal. | Pass |  | screenshots_2026-05-22/19_admin_edit_listing.png | RowActions menu closes on blur after 150 ms — programmatic clicks must dispatch mousedown+click. Real mouse users are unaffected. | QA Bot (Claude) | 2026-05-22
26 | Admin Console | Users page render | Open /user/admin/users and verify tiles + table | 1) Visit /user/admin/users 2) Check tiles: Users / Active / Disabled / Admins 3) Confirm the logged-in admin is highlighted | Tiles: 8 / 7 / 1 / 1. Row 'Admin (you)' pinned to top, Role=Admin, Status=Active. | All tiles and rows match. 'Admin (you)' row rendered with Admin role and Active status. Mock email rendered when available. | Pass |  | screenshots_2026-05-22/20_admin_users.png |  | QA Bot (Claude) | 2026-05-22
27 | Admin Console | Notifications + Mark all read | Mark all admin notifications as read | 1) Visit /user/admin/notifications 2) Read unread badge count 3) Click 'Mark all read' 4) Re-check badge and persistence | All 5 notifications are marked read in 'findroom.admin-notifications'. Badge clears. 'Mark all read' becomes disabled. | All notifications flipped to read=true in localStorage. Badge cleared. The button stays visible but is now disabled — UX behaves correctly. | Pass |  | screenshots_2026-05-22/21_admin_notifications.png |  | QA Bot (Claude) | 2026-05-22
28 | Admin Console | Settings page render & form | Open /user/admin/settings and inspect editable sections | 1) Visit /user/admin/settings 2) Inspect: General / Listing taxonomy / Pricing defaults / Moderation / Access control | All settings sections render with prefilled values; property types and amenities chips can be removed (×). | All sections render. Default values match in-code seed (FindRoom.KH, support@findroom.kh, USD, etc.). Amenities + property types chips show × affordance. | Pass |  | screenshots_2026-05-22/22_admin_settings.png | Settings persistence wired to localStorage 'findroom.admin-settings'. | QA Bot (Claude) | 2026-05-22
29 | Admin Console | View-mode toggle (Admin → User) | Admin switches to User view via the navbar pill | 1) On /user/admin/settings click the 'User' pill 2) Confirm redirect to /explore and User chrome | Redirected to /explore. 'List room' button visible in nav, admin floating nav hidden. | Redirected to /explore. User chrome restored. View-mode preference persists across navigation. | Pass |  |  |  | QA Bot (Claude) | 2026-05-22
30 | Explore Page | Duplicate listings after admin visit | After visiting /user/admin, /explore renders every mock listing twice | 1) Log in as 12000000 (admin) 2) Visit /user/admin (any tab) 3) Navigate to /explore 4) Count rendered cards vs unique titles | Each room appears once. Counter matches the number of cards. | Originally Failed: 57 cards / 29 unique titles after admin visit. Cards `/rooms/1` and `/rooms/mock-1` both rendered the same room. Root cause: `seedMockListings()` in src/lib/admin.ts:197 writes MOCK_ROOMS into localStorage as `mock-<id>`; ExploreRooms.tsx then merged `[...localRooms, ...MOCK_ROOMS]` without de-duplication. FIX applied 2026-05-22 in src/components/ExploreRooms.tsx — canonical-id dedupe (`mock-<id>` collapses to `<id>`, localRooms wins). Re-tested: 27 cards / 27 IDs, counter 27 ✓. | Pass |  | screenshots_2026-05-22/24_fix_explore_no_duplicates.png | Before-fix evidence retained at screenshots_2026-05-22/23_bug_explore_duplicates.png for the changelog. | QA Bot (Claude) | 2026-05-22
31 | Explore Page | Regression — listing dedupe with sample seeds | Admin logged-in user with 3 sample-seeded rooms + MOCK_ROOMS + 1 user-added shows no duplicates | 1) Log in as 12000000 2) Visit /profile (triggers sample seed) and /user/admin (triggers mock seed) 3) Return to /explore 4) Compare card count vs unique IDs | Card count equals unique-id count. Counter matches card count. Same-title coincidence between sample seed and mock seed (Cozy studio near Riverside) is fine — they're distinct listings owned by different users. | 29 cards / 29 IDs / counter 29. One repeated title belongs to two distinct owners (Sokha Chan vs the logged-in admin's sample). Filter (Phnom Penh) narrowed to 20/20/20 — also clean. | Pass |  |  | Locks in the fix; guards against re-introducing the bug. | QA Bot (Claude) | 2026-05-22
32 | Responsive | Mobile layout (375×812) | Explore page on mobile viewport | 1) Set viewport 375×812 2) Visit /explore 3) Verify hero stack, single-column search, BottomNav (Home / FAB / Profile) | Hero stacks, search fields stack vertically, BottomNav visible with rounded FAB, navbar hides 'List room' button on mobile. | Layout matches: hero stacks, search fields stack, BottomNav with Home / FAB / Profile rendered. Language toggle still in navbar. | Pass |  | screenshots_2026-05-22/30_mobile_explore.png |  | QA Bot (Claude) | 2026-05-22
33 | Responsive | Mobile room detail | Room detail page on mobile viewport | 1) /rooms/1 at 375×812 2) Scroll through sections | Hero image fits viewport width, sections stack, sticky footer reachable. | Rendered as expected. Sticky bottom bar shows price + Location / Contact. | Pass |  | screenshots_2026-05-22/31_mobile_room_detail.png |  | QA Bot (Claude) | 2026-05-22
34 | Responsive | Tablet layout (768×1024) | Explore page on tablet viewport | 1) 768×1024 2) Visit /explore 3) Inspect search bar and grid | Search bar transitions to compact column layout; listing grid uses 3 columns. Navbar shows 'List room' button. | Search bar columnar with full-width fields, listing grid 3 columns. Navbar shows List room. | Pass |  | screenshots_2026-05-22/40_tablet_explore.png |  | QA Bot (Claude) | 2026-05-22
35 | Print / Export | Listing export / print | Verify export-to-PDF or print affordance | 1) Inspect room detail and admin pages for export / print buttons | Export or print button per business spec. | No print or export buttons exist in the current build. Scope confirmation needed — feature may be out-of-scope for the personal/landlord MVP. | Pending | Low |  | Confirm with PM whether print/export is in MVP scope before opening as a bug. | QA Bot (Claude) | 2026-05-22
36 | Performance | Console & network errors on initial load | Browse /explore → /rooms/1 → /profile and watch console / network | 1) Open DevTools 2) Navigate the happy path 3) Inspect console_logs and failed network | No uncaught errors, no failed network requests. | No uncaught errors detected. All image requests succeed. (Note: Firebase analytics endpoint may log a non-fatal warning when env keys are absent — informational only.) | Pass |  |  |  | QA Bot (Claude) | 2026-05-22

## Evidence Index
# | Module | Feature | Status | Screenshot path
1 | Explore Page | Initial render | Pass | screenshots_2026-05-22/01_explore_desktop.png
2 | Explore Page | Language toggle | Pass | screenshots_2026-05-22/50_explore_khmer.png
3 | Explore Page | Location filter (province + district) | Pass | screenshots_2026-05-22/03_explore_filtered_bkk.png
5 | Explore Page | Property type filter | Pass | screenshots_2026-05-22/04_property_type_open.png
6 | Explore Page | Sort by price (asc / desc) | Pass | screenshots_2026-05-22/05_sort_price_asc.png
7 | Explore Page | Map view tab | Pass | screenshots_2026-05-22/06_map_view.png
8 | Room Detail | Detail page render | Pass | screenshots_2026-05-22/07_room_detail.png
10 | Room Detail | Contact host modal | Pass | screenshots_2026-05-22/08_contact_modal.png
11 | Room Detail | Location modal — embedded map | Pass | screenshots_2026-05-22/09_location_modal.png
12 | Room Detail | Invalid room id (404) | Pass | screenshots_2026-05-22/10_room_not_found.png
13 | Auth | Open Login modal | Pass | screenshots_2026-05-22/11_login_modal.png
16 | Auth | Register tab | Pass | screenshots_2026-05-22/12_register_modal.png
17 | Profile | Profile page render + sample seed | Pass | screenshots_2026-05-22/13_profile_page.png
18 | Profile | Edit profile (name + avatar + login phone) | Pass | screenshots_2026-05-22/14_edit_profile_modal.png
19 | List Room form | Form render — required field markers | Pass | screenshots_2026-05-22/15_list_room_form.png
20 | List Room form | Empty submit validation | Pass | screenshots_2026-05-22/16_list_room_validation.png
21 | List Room form | Fees modal | Pass | screenshots_2026-05-22/17_fees_modal.png
24 | Admin Console | Rooms dashboard render | Pass | screenshots_2026-05-22/18_admin_rooms.png
25 | Admin Console | Edit listing modal | Pass | screenshots_2026-05-22/19_admin_edit_listing.png
26 | Admin Console | Users page render | Pass | screenshots_2026-05-22/20_admin_users.png
27 | Admin Console | Notifications + Mark all read | Pass | screenshots_2026-05-22/21_admin_notifications.png
28 | Admin Console | Settings page render & form | Pass | screenshots_2026-05-22/22_admin_settings.png
30 | Explore Page | Duplicate listings after admin visit | Pass | screenshots_2026-05-22/24_fix_explore_no_duplicates.png
32 | Responsive | Mobile layout (375×812) | Pass | screenshots_2026-05-22/30_mobile_explore.png
33 | Responsive | Mobile room detail | Pass | screenshots_2026-05-22/31_mobile_room_detail.png
34 | Responsive | Tablet layout (768×1024) | Pass | screenshots_2026-05-22/40_tablet_explore.png