## Overview
JOUL - 8-Week Pre-Launch Plan
Cambodia's room rental marketplace - MVP launch plan
Prep Weekend | Friday May 29 -> Sunday May 31, 2026 (Week 0)
Plan Period | Monday, June 1, 2026 -> Sunday, July 26, 2026
Total Duration | 8 weeks (56 days) + 3 prep days
Launch Day | Saturday, July 25, 2026
Strategic Window | Catching the August-October student migration peak in Phnom Penh. Most Cambodian universities and prep programs start September-November; students arrive Aug-Oct to find housing. July 25 launch positions Joul ready when the peak begins.
First Geography | Phnom Penh, near universities and popular schools
First Target University | RUPP (Royal University of Phnom Penh) - largest student population, central location, dense rental supply around campus
First Supply | Landlords near Bobe's house (warm + cold outreach)
First Demand | Students from RUPP and nearby universities and schools
ASSUMPTIONS TO VALIDATE
Tech team capacity | Plan assumes ~20-30 dev hours per week available. If less, week 1-3 tech tasks slip and we delay launch by 1 week.
Bobe + team evening capacity | Plan assumes 3 evenings/week + Saturday afternoon for outreach. If less, cold outreach goals reduce proportionally.
Warm-network landlord count | Plan assumes 5-10 warm prospects. If only 2-3, weeks 2-3 lean harder on cold outreach.
TARGETS BY LAUNCH DAY
Active landlord listings | 20+ (real rooms, real photos, real phone numbers)
Registered students / engaged users | 200+ (channel members + page followers + accounts)
Languages supported | Khmer-first, English secondary
Domain | joul.kh (or chosen alternative)
Hosting | Production-grade with HTTPS
Data persistence | Firebase Firestore + Storage (demo mode disabled)
SHEETS IN THIS WORKBOOK
1. Overview | This sheet
2. Daily Plan | All 59 days (Week 0 prep + 8 weeks) with tasks and outcomes
3. Weekly Plan | Week-by-week themes and milestones
4. Monthly Goals | June and July at a glance
5. Budget | Estimated spend by month and category (USD)
6. Launch Day Hourly | Hour-by-hour schedule for July 25
7. Roles & Responsibilities | Who owns what + RACI legend
8. Risk Register | Top risks and mitigations
9. Success Metrics | What to track during launch week
10. Launch Readiness | Final go/no-go checklist

## Daily Plan
JOUL - DAILY EXECUTION PLAN (May 29 -> July 26, 2026)
Date | Day | Week | Week Theme | Bobe's Tasks | Tech Team's Tasks | Daily Outcome / Done When | Status
May 29, 2026 | Fri | W0 | Weekend Prep - Read, Decide, Get Ready for Monday | Read this entire plan end to end. Print it or save it to your phone. Identify anything that doesn't match your reality and we'll adjust. | Read the plan. Confirm Firebase setup approach. Estimate time required for week 1 deliverables. | Both sides have read the plan. Open questions written down. | To Do
May 30, 2026 | Sat | W0 | Weekend Prep - Read, Decide, Get Ready for Monday | Lock the team. Who exactly is doing what? Send each team member their week 1 tasks in writing. Confirm everyone is committed. | Set up your local dev environment to be ready for Monday. Audit current codebase for any blockers. | Team locked. Roles confirmed. Tech ready to start. | To Do
May 31, 2026 | Sun | W0 | Weekend Prep - Read, Decide, Get Ready for Monday | Finalize the warm-network landlord list. Aim for 10 names; if you only have 5, that's fine - we work with it. Rest tonight. | Rest. Final prep on Sunday evening only if needed. | Sunday: 6 PM kickoff call (30 min) to confirm Monday's start. Everyone rested. | To Do
Jun 01, 2026 | Mon | W1 | Foundation - Real Backend Exists, Network Mapped | Send the warm-network landlord list to the team. Begin contacting your top 3 prospects today. | Create the real Firebase project under an account Bobe owns. Enable Auth, Firestore, Storage services. | Network list active. Firebase project exists with services enabled. | To Do
Jun 02, 2026 | Tue | W1 | Foundation - Real Backend Exists, Network Mapped | Call or visit your own current landlord. Ask permission to list their building's rooms as Joul's first listings. | Wire .env.local with real Firebase keys. Disable demo-mode fallback. | First warm landlord confirmed. Demo mode disabled in code. | To Do
Jun 03, 2026 | Wed | W1 | Foundation - Real Backend Exists, Network Mapped | Draft Telegram + Facebook intro messages to your 5 closest friends asking for landlord introductions. | Migrate Room reads/writes in code from MOCK_ROOMS / localStorage to Firestore. | Intro messages drafted. Firestore reads/writes working in staging. | To Do
Jun 04, 2026 | Thu | W1 | Foundation - Real Backend Exists, Network Mapped | Send the intro messages. Follow up actively on any responses. | Migrate auth flow to real Firebase (registerWithPhone, loginWithPhone using live Firebase). | 3+ warm responses received. Real auth flow working. | To Do
Jun 05, 2026 | Fri | W1 | Foundation - Real Backend Exists, Network Mapped | Schedule 2-3 warm-network landlord meetings for Saturday and Sunday. | Deploy to a staging URL (Vercel preview or Firebase Hosting). | Weekend meetings booked. Staging URL accessible. | To Do
Jun 06, 2026 | Sat | W1 | Foundation - Real Backend Exists, Network Mapped | Decide domain name (joul.kh vs alternative). Buy it. Lock brand color, logo, basic identity. | Domain + DNS configuration started. | Domain purchased. Brand identity locked. | To Do
Jun 07, 2026 | Sun | W1 | Foundation - Real Backend Exists, Network Mapped | Weekly sync 7-8pm. Review week's progress. | Smoke test: register on device A, list a room, see it from device B. | Week 1 complete. Real data flowing end-to-end on staging. | To Do
Jun 08, 2026 | Mon | W2 | First Real Listings - Real Rooms on a Real Database | Arrange first warm-network landlord visits this week (target 3-5 meetings). | Begin Firebase Storage image upload integration. | 2-3 meetings scheduled. Image upload UI in progress. | To Do
Jun 09, 2026 | Tue | W2 | First Real Listings - Real Rooms on a Real Database | First warm landlord meeting. Sit with them. List their room together. | Continue image upload work. Verify auto-occupy (already implemented by Claude Code) works against staging Firestore. | 1+ real listing live with real photos. | To Do
Jun 10, 2026 | Wed | W2 | First Real Listings - Real Rooms on a Real Database | Iterate pitch script based on first meeting. Order print of 200 pitch cards with Telegram QR. | Test auto-occupy by manipulating lastActivityAt to 8 days ago. Verify room hides. | Pitch v2 written. Cards on order. Auto-occupy verified. | To Do
Jun 11, 2026 | Thu | W2 | First Real Listings - Real Rooms on a Real Database | Second warm landlord meeting. | Firestore security rules: owner-only edit/delete on rooms; public read of available rooms. | 2+ real listings live. Security rules deployed. | To Do
Jun 12, 2026 | Fri | W2 | First Real Listings - Real Rooms on a Real Database | Third warm landlord meeting. | Set up Firebase Analytics (or Google Analytics). Verify events fire (room view, contact tap, signup). | 3+ real listings live. Analytics events firing in dashboard. | To Do
Jun 13, 2026 | Sat | W2 | First Real Listings - Real Rooms on a Real Database | Photograph any rooms that need better photos. Quality-check first 3-5 listings end to end. | Bug-fix any issues found in the first listings. | Demo state ready. 3-5 quality listings exist. | To Do
Jun 14, 2026 | Sun | W2 | First Real Listings - Real Rooms on a Real Database | Weekly sync. Review demo readiness. Decide: company registration timing. | Review and finalize Firestore data model. | Week 2 complete. Demo state confirmed ready for cold outreach. | To Do
Jun 15, 2026 | Mon | W3 | Cold Outreach Begins - Real Strangers Say Yes | Prepare for first cold outreach evening (Tuesday). Practice the pitch out loud 3x. | Production deployment on real domain (joul.kh). HTTPS active. | joul.kh live in production with real listings. | To Do
Jun 16, 2026 | Tue | W3 | Cold Outreach Begins - Real Strangers Say Yes | First cold outreach evening. Knock on 10 doors. Use the pitch script. Note every reaction. | Mobile performance pass on real Android devices. | ~2 new cold landlords. Mobile Lighthouse 80+. | To Do
Jun 17, 2026 | Wed | W3 | Cold Outreach Begins - Real Strangers Say Yes | Iterate pitch based on Tuesday's reactions. Write down 3 things to change. | Fix all P0/P1 bugs surfaced after deployment. | Pitch v3. P0/P1 bug list cleared. | To Do
Jun 18, 2026 | Thu | W3 | Cold Outreach Begins - Real Strangers Say Yes | Second cold outreach evening. 10 doors. | Continue bug fixes. Address any analytics gaps. | ~2 more cold landlords. | To Do
Jun 19, 2026 | Fri | W3 | Cold Outreach Begins - Real Strangers Say Yes | Create Joul Facebook page and Telegram channel. Post first 3 content pieces (intro, behind-the-scenes, first listing showcase). | Lock the production deployment process. Document it. | Social channels live with 3+ posts. Deployment runbook written. | To Do
Jun 20, 2026 | Sat | W3 | Cold Outreach Begins - Real Strangers Say Yes | Third cold outreach session (Saturday afternoon). 10 doors. | Quick check on production stability. Monitor for errors. | ~2 more cold landlords. | To Do
Jun 21, 2026 | Sun | W3 | Cold Outreach Begins - Real Strangers Say Yes | Weekly sync. Review: total doors knocked, conversion rate, common objections. Refine script for week 4. | Review production error logs from the week. | Week 3 complete. Running landlord total: 9-11. Pitch v4 ready. | To Do
Jun 22, 2026 | Mon | W4 | Mid-Point Reality Check - Honest Assessment, Course-Correct | Continue cold outreach (10 doors). | Implement the search filters that ship at launch (price range, area, property type). | ~2 more landlords. Filters in staging. | To Do
Jun 23, 2026 | Tue | W4 | Mid-Point Reality Check - Honest Assessment, Course-Correct | Reach out to the first university student services office. Request a meeting. | Set up daily Firestore backup. Test restore procedure. | University meeting requested. Backups running daily. | To Do
Jun 24, 2026 | Wed | W4 | Mid-Point Reality Check - Honest Assessment, Course-Correct | Lock the student recruitment plan: which 5 Facebook groups, which 3 Telegram channels, which 2 universities to target. | Begin load testing with simulated 100 concurrent users. | Student plan documented. Load test results in hand. | To Do
Jun 25, 2026 | Thu | W4 | Mid-Point Reality Check - Honest Assessment, Course-Correct | Cold outreach evening (10 doors). | Address any load-testing issues. | ~2 more landlords. Load issues resolved. | To Do
Jun 26, 2026 | Fri | W4 | Mid-Point Reality Check - Honest Assessment, Course-Correct | Draft Terms of Service + Privacy Policy (Khmer + English, 1 page each). | Document the deployment process so any team member can deploy. | ToS draft v1 ready. Deployment doc complete. | To Do
Jun 27, 2026 | Sat | W4 | Mid-Point Reality Check - Honest Assessment, Course-Correct | Cold outreach session (Saturday afternoon, 10 doors). | Continue load testing if needed. | ~2 more landlords. | To Do
Jun 28, 2026 | Sun | W4 | Mid-Point Reality Check - Honest Assessment, Course-Correct | MID-POINT REVIEW. Honest assessment: on track for July 25 launch? If below 10 landlords, course-correct now. | Strategic review with Bobe. Identify any features that need to be cut. | Week 4 complete. Running total: 13-15 landlords. Course-correction decisions made. | To Do
Jun 29, 2026 | Mon | W5 | Student Side Activated - Demand Starts to Gather | Cold outreach evening (10 doors). | Final QA pass with 5 internal testers using real devices. | ~2 more landlords. QA report written. | To Do
Jun 30, 2026 | Tue | W5 | Student Side Activated - Demand Starts to Gather | Post in first 2 Phnom Penh student Facebook groups. Frame as 'free help finding rooms near your university'. | Performance optimization: page load <3s on Cambodian 4G. | First student-side posts live. Performance target met. | To Do
Jul 01, 2026 | Wed | W5 | Student Side Activated - Demand Starts to Gather | Join 3 Telegram student channels. Engage organically by answering questions first. Don't spam. | All admin tools tested end-to-end. | Telegram engagement begun. Admin tools verified. | To Do
Jul 02, 2026 | Thu | W5 | Student Side Activated - Demand Starts to Gather | Visit RUPP or chosen university campus. Photograph bulletin boards. Observe student traffic. Identify flyering opportunities. | Set up Sentry (or alternative) error monitoring. | Campus intel gathered. Error monitoring live. | To Do
Jul 03, 2026 | Fri | W5 | Student Side Activated - Demand Starts to Gather | Cold outreach evening. Post in 3 more student Facebook groups. | Address any monitoring alerts. Tighten security rules if needed. | ~2 more landlords. Student posts in 5 groups total. | To Do
Jul 04, 2026 | Sat | W5 | Student Side Activated - Demand Starts to Gather | Cold outreach session. Begin registering first 5 student 'early renters' personally. | Final tech polish on Khmer language strings. | 16-18 landlords total. 5+ student accounts created. | To Do
Jul 05, 2026 | Sun | W5 | Student Side Activated - Demand Starts to Gather | Weekly sync. Decide exact launch date (Saturday July 25 most likely). Decide launch announcement plan in detail. | Plan soft-launch deployment for Monday. | Week 5 complete. Launch date locked: Saturday July 25, 2026. | To Do
Jul 06, 2026 | Mon | W6 | Soft Launch - Real Users Find Real Problems First | Send soft-launch invites to 30-50 trusted users (friends, family, classmates, early student contacts). | Soft-launch mode active. Site publicly accessible but not promoted. Bug bash begins. | 30-50 invites sent. Soft-launch live. | To Do
Jul 07, 2026 | Tue | W6 | Soft Launch - Real Users Find Real Problems First | Personal call or message with 5 soft-launch users. Walk through their experience step by step. | Add a 'Report a problem' form to the site. | 5 user conversations documented in writing. | To Do
Jul 08, 2026 | Wed | W6 | Soft Launch - Real Users Find Real Problems First | Personal call or message with 5 more soft-launch users. | Bug triage on issues reported so far. Daily fix cycle begins. | 10 user conversations total. First bug fixes deployed. | To Do
Jul 09, 2026 | Thu | W6 | Soft Launch - Real Users Find Real Problems First | Document all confusion / bugs / 'I didn't understand X' from user conversations. | Continue urgent bug fixes. | User feedback log complete and prioritized. | To Do
Jul 10, 2026 | Fri | W6 | Soft Launch - Real Users Find Real Problems First | Decide with tech team: which bugs are launch blockers; which can ship as v1.1. | Lock the launch-blocker bug list. Begin focused sprint on those. | Launch-blocker list finalized. | To Do
Jul 11, 2026 | Sat | W6 | Soft Launch - Real Users Find Real Problems First | Cold outreach session (10 doors). Aim for 18-20 active landlords. | Continue fixing launch-blocker bugs. | 18-20 landlords total. | To Do
Jul 12, 2026 | Sun | W6 | Soft Launch - Real Users Find Real Problems First | Weekly sync. GO / NO-GO decision for public launch. | Status update on launch-blocker progress. | Week 6 complete. GO decision confirmed (or course-correct). | To Do
Jul 13, 2026 | Mon | W7 | Hard Launch Prep - Everything Ready, Everyone Rested | Order final printed cards and flyers (final design with real domain and QR). | Fix all remaining launch-blocker bugs from soft launch. | Final materials on order. Launch blockers cleared. | To Do
Jul 14, 2026 | Tue | W7 | Hard Launch Prep - Everything Ready, Everyone Rested | Press / influencer outreach: identify 3-5 local Khmer Telegram channels or Facebook pages that might cover the launch. | Monitoring dashboards live. Visible metrics: DAU, signups, listings, contact taps. | Press list ready. Dashboards live. | To Do
Jul 15, 2026 | Wed | W7 | Hard Launch Prep - Everything Ready, Everyone Rested | Draft launch announcement post in Khmer (and English version). | Disaster recovery rehearsal - simulate Firebase outage. Document recovery steps. | Launch post ready. DR runbook tested. | To Do
Jul 16, 2026 | Thu | W7 | Hard Launch Prep - Everything Ready, Everyone Rested | 30-minute call with each of the first 5 landlords confirming they're ready and excited. | Final security review - security rules tight, no exposed API keys, rate limiting on signups. | Landlords confirmed. Security review passed. | To Do
Jul 17, 2026 | Fri | W7 | Hard Launch Prep - Everything Ready, Everyone Rested | FINAL GO / NO-GO MEETING. Confirm launch on Saturday July 25. | Final tech check. Confirm everything is green. | GO decision confirmed. Launch is on. | To Do
Jul 18, 2026 | Sat | W7 | Hard Launch Prep - Everything Ready, Everyone Rested | Rest day. Light prep only. Eat well, sleep early. | On-call only. Light monitoring. | Team rested. | To Do
Jul 19, 2026 | Sun | W7 | Hard Launch Prep - Everything Ready, Everyone Rested | Weekly sync. Lock launch day hour-by-hour plan. Final landlord push if needed (target 22-25). | Final deployment freeze. No more code changes until after launch. | Week 7 complete. Running total: 22-25 landlords. Plan locked. | To Do
Jul 20, 2026 | Mon | W8 | Public Launch - Hands On, Eyes Open, Respond Fast | Soft pre-announcement on Telegram + Facebook: 'Joul launches this Saturday'. | Final QA: register, login, list-room, contact-landlord all work flawlessly. | Pre-announcement live. | To Do
Jul 21, 2026 | Tue | W8 | Public Launch - Hands On, Eyes Open, Respond Fast | Personal call to each of 20+ landlords. Confirm their listings are active and they'll respond to inquiries Saturday. | On-call. Monitor. | All landlords confirmed available for Saturday. | To Do
Jul 22, 2026 | Wed | W8 | Public Launch - Hands On, Eyes Open, Respond Fast | Daily content posts begin (Telegram + Facebook). Tone: friendly, local, excited but not desperate. | On-call. Monitor. | Content cadence active. | To Do
Jul 23, 2026 | Thu | W8 | Public Launch - Hands On, Eyes Open, Respond Fast | Final QA pass from a fresh device with team. Test every flow. | Final QA execution. | Pre-launch QA pass complete. | To Do
Jul 24, 2026 | Fri | W8 | Public Launch - Hands On, Eyes Open, Respond Fast | REST DAY. Sleep early. No major work. | On-call. Light monitoring. | Team energized for launch day. | To Do
Jul 25, 2026 | Sat | W8 | Public Launch - Hands On, Eyes Open, Respond Fast | LAUNCH DAY. 8am systems check. 9am launch post. Monitor and respond 10am-10pm. Evening team sync. | Live monitoring all day. Hot-fix any issues immediately. | Launch executed. Day-one metrics captured. | To Do
Jul 26, 2026 | Sun | W8 | Public Launch - Hands On, Eyes Open, Respond Fast | Run first targeted Facebook ads to Phnom Penh students. Cold outreach to 10 more potential landlords. | Live monitoring. Address any day-two issues. | Momentum sustained. Week 8 complete. Launch successful. | To Do

## Weekly Plan
JOUL - WEEKLY MILESTONES
Week | Dates | Theme | Key Deliverables | Landlord Target | Top Risk
W1 | Jun 1 - Jun 7 | Foundation: real backend exists, network mapped | Real Firebase project live. Firestore data layer wired. Auth migrated. Domain purchased. Brand identity locked. Warm-network landlord list of 10+ names. | 1-3 | Firebase setup takes longer than expected
W2 | Jun 8 - Jun 14 | First real listings on a real database | Image upload to Firebase Storage. Auto-occupy deployed. Security rules live. Analytics firing. 3-5 real landlord listings live with photos. Pitch script v2. 200 pitch cards on order. | 3-5 | Landlord conversations take longer than 20 minutes
W3 | Jun 15 - Jun 21 | Cold outreach begins - strangers say yes | Production deployment on joul.kh. Mobile performance pass. Facebook page + Telegram channel created with first content. 30 doors knocked. Pitch v3 + v4. | 9-11 | Cold conversion below 1-in-5
W4 | Jun 22 - Jun 28 | Mid-point reality check - honest assessment | Search filters live. Daily Firestore backup. Load testing complete. ToS draft v1. Student recruitment plan locked. Mid-point go/no-go review. | 13-15 | Behind on landlord count by week 4
W5 | Jun 29 - Jul 5 | Student side activated - demand starts to gather | Final QA pass. Performance optimized (<3s on 4G). Posts in 5 student Facebook groups. 3 Telegram channels engaged. 5+ early student renters registered. Launch date locked. | 16-18 | Student channels don't grow organically
W6 | Jul 6 - Jul 12 | Soft launch - real users find real problems first | Soft launch live. 30-50 invited testers. 10 personal user conversations documented. Launch-blocker bug list. Go/No-Go for public launch. | 18-20 | Critical bug requires significant rework
W7 | Jul 13 - Jul 19 | Hard launch prep - everything ready, everyone rested | Launch-blocker bugs fixed. Monitoring dashboards live. DR rehearsal done. Security review passed. Final printed materials in hand. Launch post written. FINAL GO/NO-GO meeting Friday. | 22-25 | Founder burnout / last-minute critical bug
W8 | Jul 20 - Jul 26 | PUBLIC LAUNCH - hands on, eyes open, respond fast | Pre-announcement Mon. Landlord confirmations Tue. Daily content Wed. Final QA Thu. Rest Fri. LAUNCH Saturday July 25. Sustain Sunday with paid ads + more outreach. | 25+ (launch day live) | Launch day downtime or major UX confusion

## Monthly Goals
JOUL - MONTHLY GOALS
| JUNE 2026 (Build & Seed) | JULY 2026 (Polish & Launch)
Theme | Get the real backend live and seed the first half of the landlord network | Polish the product, activate the student side, and execute a clean public launch
Tech Goal | Move from localStorage demo to Firestore + Storage. Production deployment on real domain. Auto-occupy live. Analytics firing. | All launch-blocker bugs fixed. Monitoring dashboards live. DR tested. Security reviewed. Launch deployment frozen.
Business Goal - Landlords | End of June target: 13-15 active landlords (warm + cold combined). | End of July target: 25+ active landlords by launch day. Final push in weeks 7-8.
Business Goal - Students | Lock the student recruitment plan in week 4. Identify universities and channels. | Activate student-side outreach. Register first 5+ early renters. Hit 200+ engaged students by launch.
Marketing | Facebook page + Telegram channel created mid-month. First content cadence established. | Launch announcement drafted. Press/influencer outreach in week 7. Public launch posts week 8.
Operations | Weekly Sunday sync rhythm established. Pitch script iterated 4x. | Daily standup in launch week. Bug triage cadence. Rest days respected (Friday before launch).
Critical Milestone | Sun Jun 28 - Mid-point honest review. Course-correct if behind. | Fri Jul 17 - Final Go/No-Go meeting. Sat Jul 25 - PUBLIC LAUNCH.
If We're Behind | Reduce launch landlord target from 20 to 15. Or push launch by 1 week. | Identify minimal launchable feature set. Cut non-essential features to v1.1 post-launch.

## Budget
JOUL - BUDGET ESTIMATE (USD)
Estimated pre-launch spend. Adjust to actual costs once quotes are received.
Category | May-June | July | Total | Notes
INFRASTRUCTURE
Domain registration (.kh annual) | 30 | 0 | 30 | joul.kh or alternative. Renewed annually.
Firebase hosting + Firestore (Spark/Blaze) | 0 | 5 | 5 | Free tier should cover MVP. Blaze plan ~$5/mo if exceeded.
Firebase Storage (images) | 0 | 5 | 5 | Free tier handles ~5GB. Budget for overflow.
Error monitoring (Sentry free tier) | 0 | 0 | 0 | Free tier sufficient for MVP traffic.
MARKETING + OUTREACH
Printed pitch cards (A6 + Telegram QR) | 30 | 20 | 50 | 200 cards initial print + 100 reprint in July.
Printed flyers for campus / dorms | 0 | 25 | 25 | 200 A6 flyers for student-side outreach.
Facebook ads (student targeting) | 0 | 150 | 150 | Test budget Jul 5-25. Phnom Penh student demographic.
Telegram channel boost (if needed) | 0 | 30 | 30 | Optional. Only if organic growth stalls.
Press / influencer outreach (gifts) | 0 | 20 | 20 | Small gestures for local Telegram channel admins.
LEGAL + ADMIN
Local lawyer review (ToS / Privacy) | 100 | 0 | 100 | Cambodian lawyer, 1-hour consultation. Recommended.
Company registration (if you decide to register) | 200 | 0 | 200 | Optional pre-launch. Can defer to post-traction.
CONTINGENCY
Buffer for unexpected (10%) | 40 | 30 | 70 | Phone bills, transport for outreach, food during launch day.
TOTAL | 400 | 285 | 685
Notes:
- All figures are estimates. Actual costs depend on Cambodian market rates and your specific choices.
- This budget assumes lean execution: founders self-fund, no salaried hires, free tier services maximally used.
- If you decide to apply for grants (Smart Axiata SmartStart, Khmer Enterprise, Techo Startup Center), do that in parallel.

## Launch Day Hourly
JOUL - LAUNCH DAY: SATURDAY, JULY 25, 2026
Hour-by-hour execution. Adjust to your team's actual roles.
Time | Action | Owner | Status
7:00 AM | Wake up. Light breakfast. Confirm internet stable. | Everyone | To Do
8:00 AM | Tech team systems check: Firebase, Firestore, Storage, domain, HTTPS. All green. | Tech Team | To Do
8:30 AM | Bobe walks through a full user flow on a fresh device. Sign up. List a room. Contact a landlord. | Bobe | To Do
8:45 AM | Final sanity check on landlord listings - all live, all set to Available. | Bobe | To Do
9:00 AM | LAUNCH POST live on Facebook page and Telegram channel. Bobe's personal accounts also post. | Bobe | To Do
9:05 AM | Pre-arranged friends and supporters share the launch post on their personal accounts. | Supporters | To Do
9:30 AM | First metrics check - site uptime, page load, signups in last 30 min. | Tech Team | To Do
10:00 AM | First wave of organic traffic expected. Monitor inbound questions in Telegram channel. | Bobe | To Do
10:30 AM | Respond to first inquiries within 30 minutes each. Note common questions. | Bobe | To Do
11:00 AM | Mid-morning sync (15 min). What's working? What's breaking? | Everyone | To Do
12:00 PM | Lunch break (rotating). Someone always on duty monitoring. | Everyone | To Do
1:00 PM | Afternoon push - share launch post in 5 Phnom Penh student Facebook groups. | Bobe | To Do
2:00 PM | Daily metrics snapshot - record DAU, signups, listings, contact taps so far. | Tech Team | To Do
3:00 PM | Personally message 5 landlords asking 'any inquiries today?' | Bobe | To Do
4:00 PM | Mid-afternoon sync. Triage any bugs reported. | Everyone | To Do
5:00 PM | Light dinner. Energy management matters today. | Everyone | To Do
6:00 PM | Evening push - Telegram broadcast + Facebook post update on launch numbers. | Bobe | To Do
7:00 PM | Respond to any backlog of inquiries. | Bobe | To Do
8:00 PM | Hot-fix any critical bugs identified during the day. | Tech Team | To Do
9:00 PM | End-of-day metrics snapshot. Capture for Sunday review. | Tech Team | To Do
10:00 PM | Day-one team sync (30 min). What worked? What broke? Priority for tomorrow. | Everyone | To Do
10:30 PM | Sleep. Tomorrow is half of the launch weekend. | Everyone | To Do

## Roles
JOUL - ROLES & RESPONSIBILITIES
Legend: Lead = primary owner, makes the decision and the time ¦ Support = assists the Lead ¦ Input = consulted but not on the hook ¦ Both = jointly accountable
Activity | Bobe | Tech Team | Shared
Product vision and roadmap | Lead | Input
Backend architecture (Firebase setup, security rules) |  | Lead
Frontend code and UI components | Input | Lead
Database / data model decisions | Input | Lead
Hosting, deployment, infrastructure |  | Lead
Bug fixing and QA | Support | Lead
Brand identity (logo, colors, copy) | Lead
Pitch script (landlord-facing) | Lead
Warm-network landlord outreach | Lead
Cold-door landlord outreach | Lead | Support
Student-side recruitment (Facebook, Telegram, university) | Lead
Content creation (Facebook page, Telegram channel posts) | Lead
Customer support / user inquiries | Lead | Support
Analytics setup | Input | Lead
Analytics review and decisions | Lead | Support
Terms of Service / Privacy Policy | Lead
Company registration / legal | Lead
Weekly Sunday sync facilitation |  |  | Both
Mid-week Wednesday check-in |  |  | Both
Mid-point review (June 28) |  |  | Both
Soft launch user testing | Lead | Support | Both
Go/No-Go decisions (July 12, July 17) |  |  | Both
Launch day execution |  |  | Both
Daily standup in launch week |  |  | Both
Post-launch retro |  |  | Both

## Risk Register
JOUL - RISK REGISTER
# | Risk | Likelihood | Impact | Mitigation | Owner
1 | Firebase migration takes longer than estimated, slipping the tech timeline by 1-2 weeks | Medium | High | Tech team starts in week 1, not week 2. Buffer built into week 2. Daily progress check during week 1. | Tech Team
2 | Cold landlord conversion below 1-in-5 - pitch isn't landing with strangers | Medium | High | Pitch iteration every week based on real reactions. Role-play with team. If hit week 4 below 10 landlords, change geography or tactics. | Bobe
3 | Student channels don't grow organically - supply gathered but no demand | Medium | High | Start social/Telegram in week 3 (not week 5). Be ready to invest in paid Facebook ads if organic isn't working by week 5. | Bobe
4 | Critical bug surfaces during soft launch requiring significant rework | Medium | High | Build a hot-fix process in week 6. Don't promise instant fixes - promise transparency. Be willing to delay launch by 1 week rather than launch broken. | Tech Team
5 | Founder / team burnout in the final 2 weeks | High | High | Respect the weekly sync rhythm. Take Saturday off after Friday cold-outreach evenings. Mandatory rest day on Friday July 24. Eat real meals. Sleep early. Burnout has killed more startups than competition - treat rest as a deliverable. | Bobe
6 | Landlord drops out at the last minute (changes mind, sells building, etc.) | High | Medium | Build a waitlist of 5 backup landlords. Target 22-25 active by week 7 (above the 20 minimum). Don't depend on any single landlord. | Bobe
7 | Launch day downtime or major performance issue | Low | High | Disaster recovery rehearsal in week 7. Monitoring dashboards live. Tech team on standby all launch day. Hot-fix process ready. | Tech Team
8 | Mid-point review reveals we're significantly behind schedule | Medium | Medium | Honest review on Sun June 28. Be willing to reduce scope (launch target 15 instead of 20) or delay launch by 1 week. Don't pretend we're on track if we're not. | Shared
9 | Scam or fraudulent listings damage early trust | Low | High | Manual review of all listings in weeks 1-4. User reporting mechanism. Landlord phone verification on signup. | Bobe
10 | Competitor copies the platform after seeing it work | Low | Medium | Speed of execution is our defense. Build supply density per district. Lock multi-listing landlords in early so switching is painful. | Shared
11 | Tech team becomes unavailable / capacity issue | Low | High | Document deployment process in week 3. Backup engineering contact identified. Don't depend on any single team member. | Tech Team
12 | Photos and listing quality are poor across the platform - bad first impression | Medium | Medium | Bobe personally photographs rooms in weeks 1-2. Manual quality review of every listing before launch. Set a minimum bar: 3+ photos, complete description, valid phone. | Bobe
13 | Rainy season disrupts door-to-door outreach (June-September is rainy in Cambodia) | High | Medium | Build a rain backup plan: when it rains, switch from cold doors to phone-based outreach (call landlords from your warm list), Telegram/Facebook prospecting, or content creation. Don't lose the evening entirely. | Bobe
14 | Bobe's network turns out to be smaller than expected (under 5 warm landlords) | Medium | Medium | Plan B: shift cold outreach to start in week 2 instead of week 3. Lower expectations slightly. Use the soft launch crew (friends/family) as your first 5-10 'demo content' rooms even if they aren't real landlords. | Bobe

## Success Metrics
JOUL - SUCCESS METRICS
What to track. Update daily during launch week, weekly otherwise.
Metric | Target by Launch (Jul 25) | Target Day 30 (Aug 24) | How to Track
Active landlord listings | 20+ | 50+ | Firestore count of rooms with status=Available
Total registered users | 100+ | 1,000+ | Firebase Auth user count
Telegram channel members | 100+ | 500+ | Telegram channel subscriber count
Facebook page followers | 100+ | 500+ | Facebook page insights
Daily active users (DAU) | 50+ on launch day | 200+ daily average | Firebase/GA Analytics
Listings viewed per day | 200+ on launch day | 1,000+ daily | Analytics - room_view event
Contact button taps per day | 20+ on launch day | 100+ daily | Analytics - contact_tap event
Estimated rentals (via follow-up) | 5+ by Aug 24 | 20+ by Aug 24 | Manual: monthly phone survey of users
Site uptime | 99.5%+ | 99.5%+ | Monitoring dashboard
Median page load (mobile 4G) | Under 3 seconds | Under 2 seconds | Lighthouse or analytics
Bugs reported per week | Under 5 | Under 2 | Report-a-problem form submissions
Pitch conversion rate (cold) | 1 in 5 doors | 1 in 4 doors | Tally during outreach evenings

## Launch Readiness
JOUL - LAUNCH READINESS CHECKLIST
Every item must be checked before public launch on Saturday July 25, 2026
# | Requirement | Status | Owner / Note
TECH
1 | Joul running on real domain (joul.kh) with HTTPS | [ ] Not yet
2 | Firebase Firestore is the live data layer for rooms and users | [ ] Not yet
3 | Firebase Storage handles all image uploads | [ ] Not yet
4 | Demo-mode localStorage fallback is disabled in production | [ ] Not yet
5 | Auto-occupy feature tested end-to-end | [ ] Not yet
6 | Auth flow tested with real Firebase users from multiple devices | [ ] Not yet
7 | Firestore security rules deployed: owner-only write, public read of Available | [ ] Not yet
8 | Daily Firestore backup running and tested with a restore | [ ] Not yet
9 | Production monitoring dashboards live (DAU, signups, listings, errors) | [ ] Not yet
10 | Error monitoring (Sentry or equivalent) reporting in real time | [ ] Not yet
11 | Page load under 3 seconds on Cambodian 4G (tested on real device) | [ ] Not yet
12 | Mobile Lighthouse score 80+ | [ ] Not yet
13 | No exposed API keys in client code | [ ] Not yet
14 | Rate limiting on signup to prevent spam | [ ] Not yet
15 | Deployment process documented (any team member can deploy) | [ ] Not yet
BUSINESS
16 | 20+ active landlord listings (real rooms, real photos, real phone numbers) | [ ] Not yet
17 | Each listing has 3+ photos, complete description in Khmer, valid contact | [ ] Not yet
18 | 200+ engaged students (channel members + page followers + accounts) | [ ] Not yet
19 | Khmer UI confirmed by 5+ native testers | [ ] Not yet
20 | Telegram channel has 4+ weeks of content history | [ ] Not yet
21 | Facebook page has 4+ weeks of content history | [ ] Not yet
22 | Pitch script v4+ tested in the field | [ ] Not yet
23 | 200+ pitch cards printed and ready | [ ] Not yet
24 | Launch announcement post written (Khmer + English) and scheduled | [ ] Not yet
25 | Press / influencer list ready (3-5 contacts) | [ ] Not yet
OPERATIONS / LEGAL
26 | Terms of Service live on the site (Khmer + English), reviewed by a local Cambodian lawyer | [ ] Not yet
27 | Privacy Policy live on the site (Khmer + English), reviewed by a local Cambodian lawyer | [ ] Not yet
28 | Incident response plan written (who to call when something breaks) | [ ] Not yet
29 | Hot-fix process documented | [ ] Not yet
30 | Backup landlords identified (5 waitlist) | [ ] Not yet
31 | Team rest day (Friday July 24) confirmed | [ ] Not yet
32 | Launch day hourly plan locked | [ ] Not yet